## Actual Plan
WEEK 0 | 2022-03-21 | DAY 0 | INTRODUCTION AND ASSESSMENT | Completed
| 2022-03-22 | DAY 1 | REQUIREMENT PHASE | Completed
| 2022-03-23 | DAY 2 |  | Completed
| 2022-03-24 | DAY 3 | DESIGN PHASE | Completed
| 2022-03-25 | DAY 4 |  | Completed
WEEK 1 | 2022-03-28 | DAY 5 | DESIGN PHASE | Completed
| 2022-03-29 | DAY 6 |  | Completed
| 2022-03-30 | DAY 7 | CODING AND TESTING PHASE | Completed
| 2022-03-31 | DAY 8 |  | Completed
| 2022-04-01 | DAY 9 | PROJECT MANAGEMENT | Completed
| 2022-04-02 | DAY 10 | PROJECT KICKOFF | Completed
WEEK 2 | 2022-04-04 | DAY 11 | SPRINT 0 - Requirements Phase | Completed
| 2022-04-05 | DAY 12 |  | Completed
| 2022-04-06 | DAY 13 |  | Completed
| 2022-04-07 | DAY 14 |  | Completed
| 2022-04-08 | DAY 15 |  | Completed
| 2022-04-09 | DAY 16 | SPRINT 1 - Design Phase | Completed
WEEK 3 | 2022-04-11 | DAY 17 | SPRINT 1 - Design Phase | Completed
| 2022-04-12 | DAY 18 |  | Completed
| 2022-04-13 | DAY 19 |  | Completed
WEEK 4 | 2022-04-20 | DAY 20 | SPRINT 1 - Design Phase | Completed
| 2022-04-21 | DAY 21 |  | Completed
| 2022-04-22 | DAY 22 | SPRINT 2 - Coding Phase | Completed
| 2022-04-23 | DAY 23 |  | Completed
WEEK 5 | 2022-04-25 | DAY 24 | SPRINT 2 - Coding Phase | Completed
| 2022-04-26 | DAY 25 |  | Completed
| 2022-04-27 | DAY 26
| 2022-04-28 | DAY 27 | SPRINT 3 - Coding Phase
| 2022-04-29 | DAY 28
| 2022-04-30 | DAY 29
WEEK 6 | 2022-05-05 | DAY 30 | SPRINT 3 - Coding Phase
| 2022-05-06 | DAY 31
| 2022-05-07 | DAY 32 | SPRINT 4 - Testing Phase
WEEK 7 | 2022-05-09 | DAY 33 | SPRINT 4 - Testing Phase
| 2022-05-10 | DAY 34
| 2022-05-11 | DAY 35
| 2022-05-12 | DAY 36
| 2022-05-13 | DAY 37 | SPRINT 5 - Finalizing Phase
| 2022-05-14 | DAY 38
WEEK 8 | 2022-05-16 | DAY 39 | SPRINT 5 - Finalizing Phase
| 2022-05-17 | DAY 40
| 2022-05-18 | DAY 41
| 2022-05-19 | DAY 42 | PROJECT REVIEW
| 2022-05-20 | DAY 43
| 2022-05-21 | DAY 44

## Revised Plan
Day | Date | Phase | Work
Monday | 2022-05-09 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Tuesday | 2022-05-10 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Wednesday | 2022-05-11 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Thursday | 2022-05-12 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Friday | 2022-05-13 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Saturday | 2022-05-14 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Week 20 | 2022-05-14 | Status | Send the status as per the given table
Sunday | 2022-05-15 | LEAVE
Monday | 2022-05-16 | Coding Phase | Angular and Web API Integration | Yes
Tuesday | 2022-05-17 | Coding Phase | Angular and Web API Integration | Yes
Wednesday | 2022-05-18 | Coding Phase | Angular and Web API Integration | Yes
Thursday | 2022-05-19 | Coding Phase | Angular and Web API Integration | Yes
Friday | 2022-05-20 | Coding Phase | Angular and Web API Integration | Yes
Saturday | 2022-05-21 | Coding Phase | Angular and Web API Integration | Yes
Saturday | 2022-05-21 | Coding Phase | Angular and Web API Integration | Yes
Week 21 | 2022-05-22 | Status | Send the status as per the given table
Monday | 2022-05-23 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Tuesday | 2022-05-24 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Wednesday | 2022-05-25 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Thursday | 2022-05-26 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Friday | 2022-05-27 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Saturday | 2022-05-28 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Week 22 | 2022-05-28 | Status | Send the status as per the given table
Sunday | 2022-05-29 | LEAVE
Monday | 2022-05-30 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing | yes(SonarQube) | No( Liniting and Coverage for angular ,Load testing,security testing)
Tuesday | 2022-05-31 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing | yes(SonarQube) | No( Liniting and Coverage for angular ,Load testing,security testing)
Wednesday | 2022-06-01 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing | yes(SonarQube) | No( Liniting and Coverage for angular ,Load testing,security testing)
Thursday | 2022-06-02 | Coding Phase | Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) | No
Friday | 2022-06-03 | Coding Phase | Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) | No
Saturday | 2022-06-04 | Coding Phase | Usability Testing - Lighthouse, https://validator.w3.org/ + Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) | No
Week 23 | 2022-06-04 | Status | Send the status as per the given table
Sunday | 2022-06-05 | LEAVE
Monday | 2022-06-06 | Testing Phase | Test Scenarios and Test Case Preparation | No
Tuesday | 2022-06-07 | Testing Phase | Test Scenarios and Test Case Preparation | No
Wednesday | 2022-06-08 | Testing Phase | Test Scenarios and Test Case Preparation | No
Thursday | 2022-06-09 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Friday | 2022-06-10 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Saturday | 2022-06-11 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Week 24 | 2022-06-11 | Status | Send the status as per the given table
Sunday | 2022-06-12 | LEAVE |  | No
Monday | 2022-06-13 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Tuesday | 2022-06-14 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Wednesday | 2022-06-15 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Thursday | 2022-06-16 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Friday | 2022-06-17 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Saturday | 2022-06-18 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Week 25 | 2022-06-18 | Status | Send the status as per the given table
Sunday | 2022-06-19 | LEAVE
Monday | 2022-06-20 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Tuesday | 2022-06-21 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Wednesday | 2022-06-22 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Thursday | 2022-06-23 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Friday | 2022-06-24 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Saturday | 2022-06-25 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Week 26 | 2022-06-25 | Status | Send the status as per the given table
Sunday | 2022-06-26 | LEAVE
Monday | 2022-06-27 | Review | Reviewing the Application of all above mentioned activities | No
Tuesday | 2022-06-28 | Review | Reviewing the Application of all above mentioned activities | No
Wednesday | 2022-06-29 | Review | Reviewing the Application of all above mentioned activities | No
Thursday | 2022-06-30 | Review | Reviewing the Application of all above mentioned activities | No
Friday | 2022-07-01 | Review | Reviewing the Application of all above mentioned activities | No
Saturday | 2022-07-02 | LEAVE
Sunday | 2022-07-03 | LEAVE
Monday | 2022-07-04 | Demo | Demostration to Training and Delivery Team
Tuesday | 2022-07-05 | Demo | Demostration to Training and Delivery Team | No
Wednesday | 2022-07-06 | Demo | Demostration to Training and Delivery Team | No
Thursday | 2022-07-07 | Summary | Refershing all the topics and Feedbacks | No
Friday | 2022-07-08 | Summary | Refershing all the topics and Feedbacks | No
Saturday | 2022-07-09 | LEAVE |  | No
Sunday | 2022-07-10 | LEAVE

## References
.NET Test Explorer | https://codemag.com/Article/2009101/Interactive-Unit-Testing-with-.NET-Core-and-VS-Code?msclkid=39ec497bd10a11ec9fc571f847c244bb
https://levelup.gitconnected.com/unit-testing-best-practices-in-net-c-3117ea4010b9?sk=5b4cdac557b3e56d97365669a12aa198
Angular - Testing | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_test.htm
Linting | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_lint.htm
Doumentation | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_doc.htm
Pipelines | https://docs.aws.amazon.com/codepipeline/latest/userguide/tutorials-four-stage-pipeline.html#tutorials-four-stage-pipeline-add-stage
Security Testing | Automated Security Testing Using OWASP ZAP with Examples! (swtestacademy.com)
Performance Testing | https://www.simplilearn.com/tutorials/jmeter-tutorial/jmeter-api-testing
https://www.youtube.com/watch?v=HiRZq9_xDjg
Code Analysis | https://www.c-sharpcorner.com/article/step-by-step-sonarqube-setup-and-run-sonarqube-scanner/

## Status Template - WEEK <No>
Work Items | Completed | In Progress | Yet to start
Low Level Design | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Web API Implementation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Angular Component Creation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Web API and Angular Integration | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Refactoring and Deployment | * Source Code Repo | * Source Code Repo | * Source Code Repo
Test Scenarios and Test Case Preparation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Application Testing and Defects Tracking and Fixing | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features

## Test Plan Template
<Project Name>Test Plan - <Cycle Number>
Scope of Test |  | Features Included | < Identify all software features and combinations of software features that will be tested.>
|  | Features Excluded | <Identify all features and significant combinations of features which will not be tested and the reasons.>
Test Deliverables |  |  | Identify the deliverable documents. You can list the following documents: - Test Plan - Test Cases - Test Incident Reports - Test Summary Reports>
Test Dependencies |  |  | <Identify significant constraints on testing, such as test-item availability, testing-resource availability, and deadlines.>
Test Environment |  | Hardware Environment | <Include the minimum hardware requirements that will be used to test the Application.>
Software Environment
Network and Communication
Test Items
S.No | Test Item |  | Source | [6 empty] | Version
Test Schedule
No. | Build | Features |  | Start Date | End Date | Actual Start Date | Actual End Date | Est Effort (in Hrs) | Actual Effort (in Hrs) | Completion % | Status
1
2
3
4
[5 empty] | Total |  | Total | 0 | 0 | #DIV/0!
Resources - Roles and Responsibilities
No. | Resource Name | Roles |  | Responsibilities
1
2
3
Depedencies
No. | Category | Description
1 | Software
2 | Resource
3 | Hardware
Assumptions
No. | Description
1
2
3

## Test Scenario Template
<Project Name><Smoke/Functional/Integration/ System/UAT> Test Scenarios
Type of Testing: Smoke/Functional/Integration/NFR/System Testing/UAT
Reference Documents :
Assumptions /Constraints :
Date : 06/07/2022
Scenario ID | Requirement ID | Module/Feature | Scenario Description
S-1 | 1 | Home | In our TMS apllication Homepage is the landing page and it is common for all users. It consists of login option
S-2 |  | Login | As a Head, he/she should be able to login to the system,after valid authentication he/she will be redirected to home page and he/she will be able to see nav bar which consists of dashboard, My Profile, Coordinator, department, trainer, trainee, reviewer.
S-3 |  | Dashboard | In the dashboard, the head is able to view his own profile and then the count of coordinator, trainer, trainee, department, Reviewer
S-4 |  | My Profile | Head is able to view his own profile
S-5 |  | Coordinator | Head is able to view, add, edit and disable coordinator
S-6 |  | Department | Head can view list of departments.
S-7 |  | Trainer | Head can view list of Trainers.
S-8 |  | Trainee | Head can view list of Trainee.
S-9 |  | Reviewer | Head can view list of Reviewer.
S-1 | 2 | Home | In our TMS apllication Homepage is the landing page and it is common for all users. It consists of login option
S-2 |  | Login | As a Coordinator, he/she should be able to login to the system,after valid authentication he/she will be redirected to home page and he will be able to see nav bar which consists of dashboard, My Profile, department, trainer, trainee, reviewer, Courses, assigned course, upcoming review, completed review
S-3 |  | Dashboard | In the dashboard, the Coordinator is able to view his own profile and then the count of trainer, trainee, department, Reviewer and courses
S-4 |  | My Profile | Coordinator is able to view his own profile
S-5 |  | Department | Coordinator can view list of departments, add, edit and disable departments
S-6 |  | Trainer | Coordinator can view list of Trainers, add, edit and disable Trainers.
S-7 |  | Trainee | Coordinator can view list of trainees, add, edit and disable Trainees.
S-8 |  | Reviewer | Coordinator can view list of Reviewers, add, edit and disable reviewers.
S-9 |  | Courses | Coordinator can view list of Courses, add, edit and disable course and inside the course he can add related topics for that course.
S-10 |  | Assign Course | Coordinator can assign a particular users to a course
S-11 |  | Upcoming review | Coordinator will schedule review to the trainee and reviewer and can add and edit the particular review
S-12 |  | Completed review | Coordinator is able to view the status of the review and they can view MOM details of the trainee who has completed review
S-1 | 3 | Home | In our TMS apllication Homepage is the landing page and it is common for all users. It consists of login option
S-2 |  | Login | As a Trainer he/she should be able to login to the system,after valid authentication he/she will be redirected to home page and he/she will be able to see nav bar which consists of dashboard, My Profile and My courses
S-3 |  | Dashboard | In the dashboard, the Trainer is able to view his own profile and then the count of courses, completed courses and progressed courses.
S-4 |  | My Profile | Trainer is able to view his own profile
S-5 |  | My Courses | Trainer can view the list of courses.Inside the course it consists of list of topics and for each topic attendence will be marked
S-1 | 4 | Home | In our TMS apllication Homepage is the landing page and it is common for all users. It consists of login option
S-2 |  | Login | As a Trainee he/she should be able to login to the system,after valid authentication he/she will be redirected to home page and he/she will be able to see nav bar which consists of dashboard, My Profile,My courses, upcoming review and completed review.
S-3 |  | Dashboard | In the dashboard, the Trainee is able to view his own profile and then the count of courses, completed courses and upcoming review
S-4 |  | My Profile | Trainee is able to view his own profile
S-5 |  | My Courses | Trainee can view the list of courses.Inside the course it consists of list of topics and for each topic attendence will be marked
S-6 |  | Upcoming review | Trainee can view the list of upcoming reviews
S-7 |  | Completed review | Trainee can view the list of completed reviews and view his own MOM
S-1 | 5 | Home | In our TMS apllication Homepage is the landing page and it is common for all users. It consists of login option
S-2 |  | Login | As a Reviewer he/she should be able to login to the system,after valid authentication he/she will be redirected to home page and he/she will be able to see nav bar which consists of dashboard, My Profile, upcoming review and completed review
S-3 |  | Dashboard | In the dashboard, the Reviewer is able to view his own profile and then the count of trainer, trainee, department, Reviewer and courses
S-4 |  | My Profile | Reviewer is able to view his own profile
S-5 |  | Upcoming review | Reviewer can view the list of upcoming reviews
S-6 |  | Completed review | Reviewer can view the list of completed reviews and view MOM of the particular trainee who has completed the review.
Other details
Author: |  |  | Team Euphoria
Reviewed by: |  |  | Team Euphoria
Approved by:
no feedback (add,view,edit)
no MOM (add,view,edit)
no assignment (add,view,edit)
Attendance(view)
flaw in mark attendance
unwanted add button in course list
Add - username pw autogenerate
unwanted edit and disable in some pages

## Test Case Template
<Project Name><Smoke/Functional/Integration/ System/UAT> Test Cases
Build/Release Version :
Type of Testing: Smoke/Functional/Integration/NFR/System Testing/UAT
Date:
Notes:
(Eg.) 1. This set of test cases should be run to check for the build fitness.
2. The tester should keep the back end (database) available and run an appropriate query to check the results / values displayed against the values shown in the front end.
Scenario ID | Test Case ID | Unit / Module or Location Description | Preconditions | Test Case Description | Test Steps | Test Data | Expected Result | Result (P/F/NT) | Defect ID | Comments
Other details
Author:
Reviewed by:
Approved by:
Test Results Reviewed by:

## Defect Log Template
Defect/Bug Report
Account/ Program Name
Project Name:
Defect Id(Required) | Defect Title | Detailed Defect Description | Related Module/Component | Defect Status | Defect Severity | Defect Priority | Defect Environment | Defect Injected Phase | Detected By | Detected in Phase | Detected in Version/Build | Defect Detected On Date | Fixed in version/Build No | Defect Category | Assigned to | Fixed on Date | Estimated Time To fix | Actual Time to Fix | Reopen Count
1 | ABC | [6 empty] | Requirements
2 | DEF | [6 empty] | Requirements
3 | GHI | [6 empty] | Analysis
4 | JKL | [6 empty] | Design
5 | MNO | [6 empty] | coding
5 | PQR | [6 empty] | Release
[26 empty] | Root cause | Communication Gap
[20 empty] | Defect Status |  | Defect Severity- | Defect Priority | Defect Environment |  |  | Lack of Domain Knowledge
[20 empty] | New |  | Critical | High | Development |  |  | Competency
[20 empty] | Open |  | Major | Critical | Integration Testing |  |  | Lack of EndUser Input
[20 empty] | Assigned |  | Minor | Medium | System Testing |  |  | Lack of Standards and Guidelines
[20 empty] | Fixed |  | Trivial | Low | Pre-Production |  |  | Environment
[20 empty] | Closed |  |  |  | UAT |  |  | Requirements not captured
[20 empty] | Rejected |  | Defect Type |  | Production |  |  | Requirements captured incorrectly
[20 empty] | Deferred |  | Review |  |  |  |  | Incomplete screen design
[22 empty] | Testing |  |  |  |  | Incorrect screen design
Incomplete database design
Incorrect database design
Incomplete report layout
Incorrect report layout
Incomplete interface definition
Incorrect interface definition
[20 empty] | Defect Injected Phase | Maintenance: | Development | Detected By | Defect Category | Missed Requirements |  | Incomplete security design
[21 empty] | Requirements | Requirements | QA |  | UI Issues |  | Incorrect security design
[21 empty] | Analysis | Design | Internal Customer |  | Functional Issues |  | Incorrect functionality
[21 empty] | Design | Coding | External Customer |  | Performance Issues |  | Incorrect / not optimized SQL
[21 empty] | coding | Release | Development |  | Non Functional |  | Incorrect logic in design
[21 empty] | Release |  |  |  | Security |  | Incomplete Unit Test Cases
[25 empty] | Environment Issues |  | Incorrect Unit Test Cases
[25 empty] | Upgrade Issue |  | Incomplete Integration Test Cases
[25 empty] | Database connectivity issues |  | Incorrect Integration Test Cases
[25 empty] | Cosmetic issues(Its Comes for Spelling Mistakes and color changes in prompts, It is like minimal changes/) |  | Incomplete Functional Test Cases
[25 empty] | Database Error |  | Incorrect Functional Test Cases
[25 empty] | Data Error |  | Code missing
[25 empty] | Typo Error |  | Incorrect logic in code
Exception handling error
Not a Defect
Incomplete Documentation
Incorrect Documentation
Scope Change
Recommendation
Incorrect Test Data