## 5-4-22
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Sharing the points on Individual User Story,Refining the Workflow | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Gokul | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Gokulraj | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Iswarya | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Kavin | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Kirubaharan | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Prathima | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Ragu | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Sruthi | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Sobhana | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30

## 6-4-22
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Discussion About User Stories And User Flow.Session With Rafi.Started Designing UI,Discussion About Estimation | Prototype,Constraints,Assumption | Acceptance criteria | 6:30 | 1:00
Gokul | trainee flow mockups, prototypes | landing page, dashboard page, courses page,attendance page, feedback page |  | rafi meeting - 1hr, team meeting - 2hr, UI templates - 2hr, total time - 5hr | figma - 1hr 30 mins, lunch & tea break - 1 hr 15 mins, total time - 2 hr15 mins
Gokulraj | Working on Constraints, Assumptions. | Discuss with Rafi about Userstory, Correction in Userstory, Discussion about Prototype, Working on Acceptance Cretiria. |  | Rafi Meeting - 1hour, Userstory - 15min, Team Disscussion - 2 hours, Prototype - 2.5 hours, Acceptance Criteria - 30min. Toatal 6.15 Hours | Figma tutorial - 30min
Iswarya | Acceptance criteria | Discussion with rafi about user story and user flow,Team discussion about prototype,UI designing. |  | 5:30 | 2:30
Kavin | Working on UI designing ,Acceptance criteria | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story |  | rafi meeting - 1hr, team meeting - 2hr, UI templates,acceptance certeria - 2.5hr, total time - 5.30hr | 2:30
Kirubaharan | Working on Acceptance criteria,constraints and Assumption | Meeting with client about user story and userflow,Team discussion about prototype | Acceptance criteria | 5:30 | 2:30
Prathima | Working on UI designing ,Acceptance criteria | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story,user flow |  | rafi meeting - 1hr, team meeting - 2hr, UI templates,acceptance certeria - 2.5hr, total time - 5.30hr | 2:30
Ragu | working on constraints, assumptions. | Discuss with Rafi about user story, correction in user story, discussion about prototype, working on acceptance cretiria. |  | Rafi Meeting - 1hour, Userstory - 15min, Team Disscussion - 2 hours, Prototype - 2.5 hours, Acceptance Criteria - 30min. Toatal 6.15 Hours | Figma tutorial - 30min
Sruthi | Acceptance criteria | Discussion with rafi about user story and user flow,Team discussion about prototype,UI designing. |  | 5:30 | 2:30
Sobhana | Working on UI designing ,Acceptance criteria,constraints | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story,user flow |  | rafi meeting - 1hr, team meeting - 2hr, UI templates - 2hr,constraints and acceptance criteria-30 min, total time - 5.30hr | 2:30
Arul | Understanding existing work done by team members

## 7-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Landing page(Trainer) | Trainer Pages( My course , Topics,Assignments,Feedback) |  | Assumption and Constraints -50mis,Meeting With rafi-45 mins,Team Discussion-50 mins,Creating UI Templates -2:15 hrs ,Total Time-4:40hrs | Session With Rafi(Builder Pattern)-30mins,Softskill Session-45 mins,others 20mins,Abstract Design Pattern-40mins ,Non Project-2:15 hrs
Gokul | prototype for trainee | Trainee requirements refining ,designed 8 pages for trainee, |  | Meeting With rafi - 45 mins,Team Discussion - 50 mins,created trainee pages - 3:00 hrs ,Total Time - 4:45 | abstratct pattern - 45 mins, lunch - 45 mins, break - 30 mins, total time -2 hrs
Gokulraj |  | Training Head - Acceptance Cretiria, Constraints, Assumptions. | Previous UI design has been discarded | Meeting with Client Rafi(About UI design)-45min, Team Discussin about UI design-60min, Making changes in Training Haed Acceptance Cretiria, Constraints, Assumptions-90min,Discussion with Teammate about Acceptance Cretiria, Constraints, Assumptions and UI design(Training Head)-60min. | Abstract Pattern Session-40min, others(lunch & tea break)-90min
Iswarya |  | UI designing on trainer - landing page,feedback page | Previous UI design has been discarded | Worked on acceptance criteria and UI design - 1:30 mins,Prototype disscussion with rafi - 45 mins,team discussion about modification on prototype - 50 mins, Trainer Landpage,feedback page-1 hr | Abstract Pattern-40 mins,Softskill Session-45 mins,
Kavin | UI design (dashboard )for training co ordinator | UI design for training Co-Ordinator | Previous UI design has been refined | Meeting with rafi (reviewed UI design )-1hr Discussion with team about UI design-1hr UI design for training Co-Ordinator-2hrs Discussion with Prathima for UI design for training Co Ordinator-1hr | Abstract Pattern Session-40min lunch,break-1.30hr
Kirubaharan |  | Assumption, Acceptance Criteria and constraints for Trainee stories | Prototype design | Discussion with team members about UI prototype - 40 mins, Worked on Acceptance criteria ,assumption and constraints for Trainee - 2 hours,Meeting with Rafi - 1 hour, | Design pattern session - 40 mins ,softskill session- 50 mins,Others - 1 hour 20 mins
Prathima | UI design (dashboard )for training co ordinator | Meeting with rafi (reviewed UI design ),acceptance criteria,containts,assumption for training co ordinator |  | Meeting with rafi (reviewed UI design )-1hr Discussion with team about UI design-1hr Completed acceptance criteria,assumption,Contraints for training co-ordination user stories.-2hrs Discussion with Kavin for UI design for training Co Ordinator-1hr | Abstract Pattern Session-40min lunch,break-1.30hr
Ragu | Landing page(Co ordinator) | Training head - UI designing ( Login page,dashboard,register page, View status page, Filter page) | Previous UI design has been discarded | Meeting with Rafi( about UI designing)- 45min, team discussion about UI designing -1hr, completed UI design for training head(Login page,dashboard,register page, View status page, Filter page)-3hrs discussion with teamate about acceptance criteria and constraints fro training head - 1hr. | Abstract pattern session - 40min lunch and break 1.30hrs
Sruthi |  | Trainer - constraints, acceptance criteria, assumptions | Previous trainer UI design has been discarded | Worked on acceptance criteria and UI design - 1:30 mins,Prototype disscussion with rafi - 45 mins,team discussion about modification on prototype - 50 mins, Trainer - constraints, acceptance criteria, assumptions - 1 hr | Session with Rafi about abstract pattern - 40 mins
Sobhana | UI design (dashboard )for training co ordinator | Meeting with rafi (reviewed UI design ),acceptance criteria,containts,assumption for training co ordinator,Refining UI for co-ordinator | Previous UI design has been discarded | Meeting with client-1hr Discussion with team about UI design-1hr acceptance criteria,assumption,Contraints for training co-ordinater for user stories.-1.30hrs UI design for training Co Ordinator-1.30hr | abstract pattern - 45 mins, lunch - 45 mins, break - 20 mins
Arul | Refining trainee user stories | Assumption, Acceptance Criteria and constraints for Trainee stories | Prototype design | Meeting with client - 45mins,I've discussed about UI protyping with team members - 45mins, Done acceptance criteria for Trainee user stories - 120 mins | Softskill Session-45 mins, Design pattern session ,others 90mins

## 8-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Trainer | Co-Ordinator(Schedule Review,attendance,Course flow),Trainee(Feedback,Assignment,Mom) |  | Workflow Integration-1 hr,Reviewing-1 hr,Meeting With Rafi-1:40 hrs,Worked On Ui For Co-ordinator-2 hrs,ui Trainer-1 hr,Total Time-6:40 hrs | Break-1 hr
Gokul | ABSENT | ABSENT |  | ABSENT | ABSENT
Gokulraj | Designing prototype | Entities and Data Model Rough |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design and Entity - 120mins, Correction in Design - 60mins | Builder Pattern Session-60min, Photo Shoot at BasketBall court - 60 mins, others(lunch & tea break)-90min
Iswarya |  | Trainer course,topic,assignment,list of trinee and their detail page UI Design |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design and Entity - 120mins, Correction in Design - 60mins
Kavin | UI design for training co ordinator and Training head refining | Training head login,register,Dashboard and List of department |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design-120 min, Training head Design - 60mins and Prepare for presentation in Adaptor pattern-60 mina | Pattern Session-60min, Photo Shoot at Volleyball court - 60 mins, others(lunch & tea break)-1.15hour
Kirubaharan |  | Trainee acceptance criteria, Constraints and assumption |  | Meeting with Rafi -50 mins,Corrections in Design - 60 mins,Team discussion about entity and design -180 mins | Builder pattern session-60 mins,Friday activities-60 mins, Others - 90 mins
Prathima | UI design (dashboard )for training co ordinator,entity framework and requirements | UI for trainee |  | Meeting with Rafi -1hr(reviewed UI Design)Corrections in Design - 1hr,Team discussion about entity and design -2hrs | Builder Design Pattern and prototype Session-1hr, Photo Shoot at basketball court - 1hr, others(lunch & tea break)-1.30hr
Ragu | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sruthi |  | ABSENT | ABSENT | ABSENT | ABSENT
Sobhana | UI design (dashboard )for training co- ordinator | UI for training coordinator | Previous UI design has been discarded | Meeting with Rafi -1hr,Corrections in Design - 1hr,Team discussion about entity and design -3hrs | Builder Design Pattern and prototype Session-1hr, Photo Shoot at basketball court - 1hr, others(lunch & tea break)-1.30hr ,review-45min
Arul | Designing prototype | Entities and Data model | Exploration | Meeting with client - 45mins,I've discussed about User flow team members - 120mins, Done entity model rough - 60 mins | Softskill -45 mins, Design pattern session ,others 90mins

## 9-4-22
- | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Entity ,Attributes | Training Co-ordinator(Review,Assignment),Consistent check in Training Co-ordinator |  | Team discussion - UI Integration -45 mins, Refining Flow Correction 2 hrs,Consistent Check-2hrs,ui design(Co-ordinator,Trainee) 2 hrs,Meeting With Rafi-1:45 hrs.Total 8:45 hrs | Break-1:00 hr
Gokul | ABSENT | ABSENT |  | ABSENT
Gokulraj | Training head and training co-ordinator refining | Training Head UI page |  | Team meeting -60mins ,Correction in UI design-2hrs, entity frame work and datamodel -90 min ,Meeting with Rafi -1.45hours(reviewed UI Design) | others(lunch & tea break)-90min
Iswarya | Data Model | Trainer course,topic,assignment,list of trinee and their detail page UI Design |  | Training co-ordinator UI Discussion-1.30 hrs and design-3hrs,Meeting with Rafi -1.30 hrs. Sunday Trainer UI correction and Design-3hrs
Kavin | UI design for training co ordinator (Assign course,review ,and attendance) | Ui design Training Co-ordinator Dashboard and create course ,assign courseand prepare for presentation in design pattern |  | Prepare for presentation in design pattern -90 min ,Meeting with client (Rafi) - 1.45hours,Team meeting -60mins | Others(lunch & tea break)-1.30hour
Kirubaharan |  | Consistency checking in Trainee, Entity modeling |  | Team discussion about UI integration - 45 mins , Entity modelling - 1 hour,consistency checking - 2 hours,review with Rafi - 100 mins | Lunch and other breaks - 1 hour 30 mins
Prathima | Entity ,Attributes | UI design for training co ordintor(schedule review),dashboard for training co-cordinator,trainee,trainer,training head, Entity framework and data model |  | Team meeting -60mins ,Correction in UI design-2hrs, entity frame work and datamodel -90 min ,Meeting with Rafi -1.45hours(reviewed UI Design) | others(lunch & tea break)-1.30hr
Ragu | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sruthi | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sobhana | UI design (dashboard )for training co- ordinator | UI for trainee and trainer |  | Group discussion about UI integration - 45 mins , Entity modelling - 1 hour,Consistency checking - 2 hours,Meeting with rafi - 1.45 mins | Lunch : 1hour, Break:20 mins
Arul |  | Entities and Data model |  | Group discussion about UI integration - 45 mins , Entity modelling - 1 hour,Consistency checking - 2 hours,Session with Rafi - 100 mins | Break-2:00 hr

## 11-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Trainer UI | Co-Ordinator(Schedule Review,attendance,Course flow),Trainee(Feedback,Assignment,Mom) |  | Workflow Integration-1 hr,Reviewing-1 hr,Meeting With Rafi-1:40 hrs,Worked On Ui For Co-ordinator-2 hrs,ui Trainer-1 hr,Total Time-6:40 hrs | Break-1 hr
Gokul | Entity relationships, Entity attributes | Completed Changes in Trainee Design, Completed changes in Trainer Design, Worked on Data Models in TMS |  | Changes in Trainee Design - 2hr,Meeting With Rafi - 1hr 30 mins, Data Models - 1hr 30 mins total hrs- 5hrs | Lunch and break 1hr 15 mins, self exploration - entity frame work - 1hr total hrs - 2 hrs 15 mins
Gokulraj | Entity, Date model and relationships | Training Head and Co-ordinator Dessign flow |  | Team Disscussion 20 mins about design flow, Worked on Training Head and co-ordinator design flow 120 mins, Meeting with client (Rafi) - 90mins, Team Discussion about Design and Entity - 20mins, Alteration in Head and Co-ordinator Design flow - 120mins | Lunch and Tea break-90min
Iswarya | Data model Relationship | Entities and Data Model Rough |  | Team discussion-15 mins,working with Data model-2hrs, Meeting with client (Rafi) - 1.30 hrs | Preparing for review-2.30hrs, Attending Review-50 mins
Kavin | UI design for training co ordinator and Trainee consistency and naming conversion | Training head login,register,Dashboard and List of department |  | Meeting with Rafi-100 minutes,Worked on Training Head naming conversion and consistency-2 hours ,Discussion with team - 20 mins | others(lunch & tea break)-1.30hour
Kirubaharan | Redifining the acceptance criteria | Reviewed acceptance criteria for Trainee ,Trainer,training coordinator,Training head, Updated MOM, Entering data in entity model |  | Discussion with team - 20 mins, Worked on entity data model for trainee and collaborated with others-120 mins,meeting with Rafi- 100 mins | Prepared for code review - 1 hour , others - 90 mins
Prathima | Entity data model operation for Trainer | Entity datamodel ,artributes,relationship for trainer |  | Discussion with team - 20 mins, Worked on entity data model for trainer -3 hours ,meeting with Rafi- 100 mins | others(lunch & tea break)-1.30hour
Ragu | Entity data model | entered sample data for head , co ordinator, trainee , trainer. |  | discussion with team -20min, reviewed the head and co ordinator UI, meeting rafi 100 mins , entering sample data for head,co ordinator, trainer , trainee - 3 hrs, editing the changes in UI ( head , co ordinator, trainer, trainee). | lunch and break 1.30hrs
Sruthi | Data model Relationship | Entities and attributes for all users |  | Team discussion-15 mins,working with Data model-2hrs, Meeting with client (Rafi) - 1.30 hrs,Prepared data model for all users - 3 hrs | Break - 1 hr
Sobhana | Entity Data model and its Relationship | Entity datamodel for all users |  | Discussion with team -20min,meeting rafi -1.30hours , Entity data model for trainee and integrated with others-3.30 hours | Lunch -45mins,Break-20 min
Arul | Redifining the acceptance criteria | Reviewed acceptance criteria for Trainee, Trainer, Training co ordinator, Trainnig Head, Entering data in entity model | Exploration | Meeting with client - 90 mins, Discussion with team - 10mins. I've decided to work on entity data model data entry - 120mins and reviewing UI flow | lunch and others 130mins

## 12-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Data model (Behaviours) | UI(Trainer) |  | Team,Discussion 30mins,iUI(Trainer)-2hrs,Meeting With Rafi-1 hr-total -3:30 hrs | session with anitha(1hr),Preaparation for Presentation-3hrs,Total-4 hrs
Gokul |  | team meeting - 30 mins,TMS data model refining - 2 hr 30 mins, Data entry in TMS - 30 mins, TMS relation ship mapping - 30 mins, rafi meeting - 1hr, MOM - 30 mins |  | 4hrs 30 mins | Lunch & break - 1hr 30 mins,teaching others - 1hr
Gokulraj | Date model, relationships and behaviour | TMS Full UI Design Flow |  | Team Disscussion 30 mins about Design Integration and Data Model, Integration on Training Head, Co-ordinator, Trainer, Trainee design flow 100 mins, Meeting with client (Rafi) - 60mins, Creating Reviewer Flow and Making Changes in Course Flow 60mins, Finalize the TMS Design Flow 120mins | Lunch and Tea break-90min
Iswarya | Class model with operations | Data models entities and attributes |  | Team meeting - 30 mins, Refining Entities and attributes for TMS - 2 hr 30 mins, rafi meeting - 1hr, MOM - 30 mins | Session with Anitha-1 hr, worked with assignments given by anitha, Break - 1:30 hrs
Kavin | Entity Date Model and Relationships | UI design Consistency for Trainee and trainer |  | Meeting with Rafi-60 minutes,Worked on Trainer, and Trainee naming conversion and consistency-2 hours ,Discussion with team - 30mins | others(lunch & tea break)-100 min
Kirubaharan | Behaviours of entity and view models | Data models entities and attributes |  | Discussion with team - 20 mins, meeting with 60 mins , Prepared MOM | Session with Anitha - 1 hour, prepared for presentation - 2 hours,Others- 1 hour 30 mins
Prathima | Entity data model operation for Trainer | Entity datamodel ,artributes for trainer |  | Team meeting - 30 mins, Refining Entities and attributes for TMS - 2 hr 30 mins, rafi meeting - 1hr, Relationship mapping - 30 mins | others(lunch & tea break)-1.30hour
Ragu | Entity data model | Full UI design completed |  | discussion with team -30min,intergation of head ,co ordinator , trainer , trainee UI-100mins, meeting rafi 60 mins , creating reviewer work flow design and editing the course list - 60mis, reviewing the full uI work flow -120min. | lunch and break 1.30hrs
Sruthi | Class model with operations | Relationship mapping |  | Team meeting - 30 mins, Refining Entities and attributes for TMS - 2 hr 30 mins, rafi meeting - 1hr, MOM - 30 mins , Relationship mapping - 30 mins | Break - 1:30 mins
Sobhana | Entity Data model and its Relationship | Entity datamodel for all users |  | Team discussion- 30 mins, Meeting with rafi - 1hr, MOM - 30 mins ,Entities and attributes for TMS - 2 hr 30 mins, Relationship mapping - 30 mins | Lunch -45mins,Break-20 min
Arul | Behaviours of entity and view models | Data entry in TMS - 30 mins, TMS relation ship mapping - 30 mins, rafi meeting - 1hr, MOM - 30 mins | Exploration | Team meeting - 30 mins, client meeting - 1hr, Refining Entities and attributes for TMS - 2 hr 30 mins,MOM - 30 mins , Relationship mapping - 30 mins | lunch and others 130mins

## 13-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Trainer (ui) | Correcting work flow of trainee and reviewing the co-ordinator. |  | team discussion 30 mins,working on ui(trainee)-1 hr and 30 mins ,meeting with rafi 30 mins,working refining data model -1 hr,working on ui reviewing and consistent check(over all)-2:30hrs ,Total-5hrs and 30 mins | break 1 hr
Gokul | TMS Physical Data Model,TMS calss diagram with operations | team meeting - 30 mins,TMS data model refining - 2 hr 30 mins, Data entry in TMS - 30 mins, TMS relation ship mapping - 30 mins, rafi meeting - 1hr |  | 4hrs 30 mins | Lunch & break - 1hr 30 mins,teaching others - 1hr
Gokulraj | Date model, relationships and behaviour | TMS Full UI Design Flow |  | Team Disscussion 30 mins about Design Integration and Data Model, Integration on Training Head, Co-ordinator, Trainer, Trainee design flow 100 mins, Meeting with client (Rafi) - 60mins, Creating Reviewer Flow and Making Changes in Course Flow 60mins, Finalize the TMS Design Flow 120mins | Lunch and Tea break-90min
Iswarya |  | Review the Entire UI and relationship of datamodel |  | Team meeting - 30 mins, Relationship for Datamodel -30 mis, Understanding the 2 different datamodel-1 hr ,Team discussion for Datamodel relationship-2hr, Review the entire UI -2hr | Lunch and tea break -1.30 mins
Kavin | UI for Trainer in TMS | UI design work flowfor Training Co-ordinator and Trainer |  | Team meeting - 1.30hr, rafi meeting - 30mins,Entity data model relationship and UI design Trainee -2hrs | others(lunch & tea break)-90min
Kirubaharan | Behaviours of entity and view models | Data models entities and attributes |  | Discussion with team - 20 mins, meeting with 60 mins , Prepared MOM | Session with Anitha - 1 hour, prepared for presentation - 2 hours,Others- 1 hour 30 mins
Prathima | Entity data model operation for TMS | Entity datamodel ,artributes for TMS |  | Team meeting - 1.30hr, rafi meeting - 30mins,Entity data model relationship ,attributes,operation-2hrs | others(lunch & tea break)-1.30hour
Ragu | Entity data model | Full UI design completed |  | discussion with team -30min,intergation of head ,co ordinator , trainer , trainee UI-100mins, meeting rafi 60 mins , creating reviewer work flow design and editing the course list - 60mis, reviewing the full uI work flow -120min. | lunch and break 1.30hrs
Sruthi |  | Review the Entire UI |  | Team meeting - 30 mins, Understanding the datamodel-1 hr ,Team discussion for Datamodel relationship-2hr, Review the entire UI -2hr | Break - 1:30 mins
Sobhana |  | Refining the data model |  | Team meeting - 30 mins, Understanding the datamodel-1 hr ,Team discussion for Datamodel relationship-2hr,Refining the data model -30 min
Arul | view model for a page | TMS physical model |  | Team discussion- 30 mins, Meeting with rafi - 1hr, MOM - 30 mins , Relationship mapping - 30 mins | lunch and others 130mins

## 15-4-22
#NAME? | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | HLD | UI(Trainer),Overall(consistent check),reviewing data model. |  | Team meet -20 mins,working on ui(over all)-3hrs,reviewing data model and convey the corrections-30mins,reviewing trainer(constraints,assumption,acceptance criteria)-30mins, | break -1:30 hrs
Gokul | angular cli exploration | TMS Physical Data Model,TMS calss diagram with operations |  | TMS Physical Data Model - 1 hr, TMS class diagram - 1 hr, TMS class diagram with operations - 1hr | angular cli cmd - 1hr 30 mins,lunch and break- 1hr
Gokulraj | Date model, relationships and behaviour | checking overall UI flow and checking flow , acceptance criteria, assumption, constraints |  | team meet 20mins, checking and editing overall UI -3hrs, checking flow , acceptance criteria, assumption, constraints (training head)- 30mis | Lunch and Tea break-90min
Iswarya |  | Refining the Trainer and Head Acceptance Criteria,constrain,assumption |  | Team meet in online-20 mins, Review the physical datamodel and class diagram-1hr, trainer and head Acceptance criteria,constrain and assumption-2hrs, review the trainig coordinator Acceptance criteria-20 mins
Kavin | HLD | UI(Trainer),Overall(consistent check) in UI prototype |  | Meeting with Rafi-60 minutes,Worked on Trainer, and Trainee naming conversion and consistency-2 hours ,Discussion with team - 30mins | others(lunch & tea break)-100 min
Kirubaharan |  | Refined acceptance criteria for trainee flow |  | Team meet - 20 mins , Reviewed acceptance criteria for trainee - 2 hours , TMS physical data model - 1 hour | Lunch - 1 hour
Prathima |  | Refining the Training coordinator Acceptance Criteria,constrain,assumption |  | Team meet in online-20 mins, Review the physical datamodel and class diagram-1hr, training coordinator Acceptance criteria,constrain and assumption-2hrs, | Lunch and Tea break-90min
Ragu | Entity data model | checking overall UI flow and checking flow , acceptance criteria, assumption, constraints |  | team meet 20mins, checking and editing overall UI -3hrs, checking flow , acceptance criteria, assumption, constraints (training head)- 30mis | lunch -1hr
Sruthi |  | Refining the Trainer and Head Acceptance Criteria,constrain |  | Team meet in online-20 mins, Review the physical datamodel and class diagram-1hr, trainer and head Acceptance criteria,constrain and assumption-2hrs, review the trainig coordinator Acceptance criteria-20 mins
Sobhana |  | Refining the Training coordinator Acceptance Criteria,constrain,assumption |  | Team meet in online-20 mins, Review the physical datamodel and class diagram-1hr, training coordinator Acceptance criteria,constrain and assumption-2hrs,
Arul | View model for a page | Physical Data model and acceptance criteria and assumption and constrains for trainee |  | Team meet - 20 mins , Reviewed acceptance criteria for trainee - 2 hours , TMS physical data model - 1 hour | lunch and others 130mins

## 18-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | HLD | Entity Framework(self exploration) |  | meeting with team-30 mins(HLD) | Preparing for review(webapi)-3 hrs,self exploration-2 hrs.total-5 hrs
Gokul | HLD | Explored Angular components, data binding, passing data from parent to child, from child to parent, life cycles of angular components etc. |  | Team discussion 30mins | angular 5hrs, typescript 30mins, lunch and break 1hr 30mins
Gokulraj | HLD for TMS | Self Exploration |  | Team discussion -30mins | Lunch and Tea break-90min,Basics and overview of Entity framework,web api,angular.
Iswarya | HLD for TMS | Self Exploration |  | 30 mins : Team discussion | 1hr : WebAPI basic 2hrs : Angular 1hr : implemented the learned concept
Kavin | HLD for TMS | Self Exploration |  | 31 mins : Team discussion | 1hr : WebAPI basic 2hrs : c# 1hr : implemented the learned concept
Kirubaharan | HLD for TMS | Explored on Angular 1 hour30 mins , Web API basics 1 hour 30 mins |  | Team meeting - 30 mins | Others ( Lunch and Tea break)-1 hour 30 mins
Prathima | HLD for TMS | Self Exploration |  | 30 mins : Team discussion | exploration on entity framework, and web API-2.30hrs
Ragu | HLD for TMS | self Exploration |  | Team discussion 30mins | lunch -1.30hr exploration on entity framework, and web API -2hrs
Sruthi | HLD for TMS | Self Exploration |  | Team discussion about Hld - 30 mins | basic concepts on angular and web api- 3 hrs, lunch break - 1 hr
Sobhana | HLD for TMS | Self Exploration |  | Team discussion about Hld - 30 mins | Lunch -45mins,Break-20 min,exploration on entity framework, web API -1.30min,Install and run the typescript code-45mins,
Arul | HLD for TMS | Exploration on Angular, Entity Framework |  | Team meeting - 30 mins | lunch and others 130mins

## 19-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | HLD(services,components),typescript exploration | HLD |  | meeting with team-30 mins(HLD),(services,components,data history)-1hr | Preparing for review-3hrs,self exploration-2 hrs.total-5 hrs
Gokul | angular exploration | system architecture |  | Team discussion 30mins, system architecture - 1 hr, reviewed data dictonary - 30mins,helped in view model - 30 mins, | angular 4hrs, lunch and break 1hr 30mins
Gokulraj | HLD for TMS | Layout for Login and Navbar |  | team meet 30mins, Html and Css Layout for Side navbar and Login page. | Review with Anitha - 60mins, Lunch and Tea break-90min,Typescript overview and basic program,
Iswarya | HLD for TMS | View Model for TMS. Non-functional Requirements in HLD |  | 30mins : Team discussion, 1hr : View model,1hr : non-functional Requirements, | 3hr : Exploring Angular 1hr: Exploring Typescript
Kavin | Absent | Absent | Absent | Absent | Absent
Kirubaharan | Angular exploration | Flow chart for Trainee flow |  | Team meeting - 30 mins | Angular 1 hour 30 mins, re explored the concepts of SQL and C# - 2 hours,Worked on assignment Given by Jaya - 1 hour 30 mins Others ( Lunch and Tea break)-1 hour 30 mins
Prathima | exploration on web api | HLD for TMS |  | Team meeting - 30 mins HLD for tms - 1 hr | Preparation for internal review - 30 min Internal review - 1 hr Lunch & Tea break - 1.5 hr Typescript overview - 30 mins
Ragu | HLD for TMS | Layout for Login and Navbar |  | team discussion - 30min, Html and css layout for sidesnavbar and login page. | lunch -1.30hr , exploring typescript.
Sruthi | HLD for TMS | View Model for TMS. Design Principles and introduction in HLD |  | Team discussion - 30 mins,View model - 1hr | Explored on angular - 2hrs,typescript - 1 hr
Sobhana | HLD for TMS | Data Model and Database discription of HLD |  | Team meeting-30 mins,Typescript-30mins,Database discription of HLD-2hrs, Exploration on Entity framework and Angular -45min | Lunch -45mins,Break-20 min
Arul | Typescript exploration | TMS logical view and Component identifing |  | Team meeting - 30 mins, Logical view of TMS - 30 mins, | lunch and others 130mins

## 20-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | ABSENT
Gokul | web api exploration | team meeting - 30 mins, Meeting with rafi 1hr, team discussion -1hr, web api - 2hr |  | 4hrs 30mins | lunch and break 1hr 30mins, clearing others doubts - 2hrs
Gokulraj | Layout for TMS |  |  | Team Discussion about HLD - 30mins, Meeting with Rafi - 45mins, Session with Rafi about Services - 35mins, Team Discussion for split the works - 30mins, Bootstrap tutorial - 120mins | Softskills - 60mins, Lunch and Tea break - 90min,
Iswarya | Interactions in HLD |  |  | 30mins : Team discussion, 45 mins : Meeting With Rafi, 35mins : Session about HLD and services, 30mins : Team discussion for splitting the topics and doubt clarification, 1 hr :System Architecture and NFA for HLD | 3omis : Component concept in Angular,1 hrs : Softskill session,1.30 mins : Break time
Kavin | Layout for TMS |  |  | Meeting with Rafi-45 Min,Team discussion for splitting the topics-60 min,Session About Services and HLD-30 min,Recall the previous day work-30 min,Bootstrap tutorial-120 min | Softskill session - 1 hr, Break - 1:15 hours
Kirubaharan |  | Created services for (Department,role) |  | Team meeting - 30mins, Meeting with Rafi-45 mins, Updated MOM,Worked on Services- 2 hours | Softskills session - 1 hours , Others (Lunch and break - 1 hour 30 mins)
Prathima | exploration on web api,angular concepts | Databse Diagram for TMS(user,course,topic,role,review,reviewstatus,department) |  | Meeting with Rafi - 45 mins Team Discussion : 1 hr Worked on DB Diagram - 2.5 hr | Soft skill session - 1hr Lunch and Teabreak-1.5hr
Ragu | Layout for TMS |  |  | team discussion on HLD-30min, meeting with rafi-45min, session on services and HLD-30min,discussion with team to split work-30min, bootstrap tutorial- 140mis. | lunch -1.30hr , desgin pattern discussion with rafi(flyweight) -60min
Sruthi | Services and dependencies in HLD | View Model for TMS. Design Principles and introduction in HLD |  | Team discussion for 30 mins, meeting with rafi for 45 mins,Session on Hld and services for 35 mins , Discussion with team for splitting topics and doubt clarification - 30 mins,Database(SQL)for tms -30 mins, Worked on system architecture and NFA for Hld for 1 hr | Softskill session - 1 hr, break - 1:30 mins
Sobhana |  | Created Database and Database Diagram for TMS(Attendance,assignment,CourseFeedback,Mom,TraineeFeedback,Momstatus,attendancestatus,assignmentstatus,CoursetraineeMapping) |  | Team discussion - 30min, Meeting with client -45 min, Worked in Database diagram-2.30min | Softskill session -1hr,Lunch -45mins,Break-20 min
Arul |  | Creating class files for services(User,Course,Review) |  | Team meeting -30 min , Client meeting - 35 mins ,Class files for services - 2 hrs, Updating MOM - 15 mins | lunch and others 90mins, Angular component binding - 1 hr, WebApi - 1hr, softskill session - 1hr

## 21-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | web api(Department) | review the services, |  | meeting with team-20mins (spliting the teams),meeting with rafi-61 mins ,meeting with team work completion-20mins,working on web api(review)-2hrs,totla time spent-3hrs 41 mins | exploring on web api(2 hrs),break-40 mins,total -2hrs 40 mins
Gokul | angular exploration | Team meeting -30 min , Client meeting - 60 mins , Team meeting - 30mins, Services and classes - 2 hrs, Angular - 3 hrs |  | 4hrs | 4hrs
Gokulraj | Layout for TMS except Head navbar | Layout for Head Navbar |  | Team Discussion about Work progress - 20mins, Meeting with Rafi - 60mins, Team Discussion for Work plan and team split - 30mins, Working and Alteration on Head Layout 140mins | Lunch and Tea break-75min
Iswarya | working on Web API | Refining System Architecture and Interaction for HLD |  | 20 mins : Team discussion, 1hr : Meeting With Rafi,30mis : Team discussion and clarifying doubts,1.30 hr : Refining System Architecture and Interaction for HLD | 1hr : Exploring about Web API and connecting the DB, 1.30 mins : Lunch and Break
Kavin | Layouts of TMS Co-ordinator | Layout for head nav bar |  | Team discussion-20 min,Meeting with Rafi-60 min,Discussion about Database diagram-30 min,Team discussion and Doubt-30 min | Lunch and Break-90 min,Boot strap about nav bar explortion-2 hours
Kirubaharan | Learning Web Api | Reviewed Services |  | Team discussion - 20 mins, Worked on Services(Department and role) - 2 hours, Meeting with Rafi - 1 hour, Doubt clarification meeting - 30 mins | Watched Web api tutorial - 1 hour , Others(lunch and break) - 1 hour
Prathima | exploration on web api | Database diagram for TMS |  | Team Discussion-20mins Review Meeting with Rafi-1hr Refining the database diagram-10mins Understanding the services and methods in services-30mins Understanding the system architecture and interaction -30mins Team Discussion-30 mins | Lunch & Tea break - 1.5 hr Exploration on Web API - 1 hr
Ragu | layout for ( co-ordinator,trainer,trainee) | layout for training head |  | team disussion (progress) -20mim, meeting with rafi-60min, team discussion (team segeration)-30min, working on layout for training head-150min | lunch -1.15hrs
Sruthi | Working in layout for TMS | System architecture for HLD |  | Team discussion - 20 mins, meeting with rafi - 1hr,Team meeting and doubt clarification- 30 mins, worked with system architecture and interactions in HLD - 1:30 hr | Explored on bootstrap - 40 mins,break - 1 hr
Sobhana | Layout for TMS | Layout for head nav bar |  | Team disussion -20mim, Meeting with rafi- 1hr, Team discussion-30min, learned bootstrap basics- 40 mins, working on layout for TMS - 1.45 mins | Lunch -35mins,Break-20 min
Arul | Building service for Department | Creating class files for all services |  | Team meeting -30 min , Client meeting - 60 mins ,Class files modification - 2 hrs, Updating MOM - 15 mins | lunch and others 90mins, how to use logger - 1hr and Scaffolding in VS code - 45 mins

## 22-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | web api(Department) | review the services, |  | working on web api(department)-1 hr ,meeting with rafi-1 hr ,meeting with team 20 mins,working on web api(deptment)-2hr,Total Time Spent-4 hrs 20 mins | mail for db remoting 20 mins,fun friday 1 hr 26 mins,break 40 mins,Total -2 hr 26 mins |  | visual studio code - .Net SDK is not found in VSCode - Stack Overflow
Gokul | Absent
Gokulraj | Layout for TMS | Footer, Head View pages(list of coordinator, trainer, trainee, reviewer) |  | Meeting with Rafi - 60mins, Working on Head Layout 120mins | Lunch and Tea break-75min
Iswarya | web API(Role) | Review the Entire Services |  | 1hr : Meeting with Rafi,20 mins : Team Meeting, 35 mins : Review the Services,30 mins : web API ef installation. | 1 hr : Chain of reponsibility,1.30 mins Fun friday,1.30 mins : lunch and break
Kavin | Layouts of TMS dashboard | Layout for Login |  | Team discussion-20 min,Meeting with Rafi-60 min,Discussion on Layout-30 min,Team discussion-30 min, Review of service-30 min | Lunch and Break-90 min,Fun friday -2 hours, Layout Exploration -1 hours
Kirubaharan | Web Api exploration |  |  | Team meeting - 30 mins,Meeting with Rafi - 1 hour, Services review - 30 mins, Created Namespace ,classes and properties in VS code - 30 mins | Friday activities - 1 hour 30 mins, Others (Lunch and break) - 1 hour 30 mins , Web api Tutorial - 1 hour
Prathima | exploration on web api |  |  | Team Discussion(to know the progress of the team )-20mins Review Meeting with Rafi-1hr web api (review service)-1hr Team Discussion-30 mins,Created Namespace ,classes and properties in VS code - 30 mins | Lunch & Tea break - 1.5 hr Fun session with Training team-1.5hr
Ragu | registration for trainee and trainer | registration for co-Ordinator |  | team disussion -30mim, meeting with rafi-60min, working on layout for registration page( head)-90min, reviewed the services-35min | lunch -1.15hrs softskill(fun friday activity) with TN team-120min
Sruthi | Working in layout for TMS | refining system architecture,review the services |  | 1hr : Meeting with Rafi,20 mins : Team Meeting, 35 mins : Review the Services | 1.30 mins Fun friday,1.30 mins : lunch and break
Sobhana | Layout for TMS | Refining Head dashboard,reviewing services |  | Team discussion -30 min,Meeting with Rafi - 1hr, Working on Head Layout -30 mins, Review the services-20 mins. | Lunch -35mins,Break-20 min,fun friday-1.30 min
Arul | Building Api for Department Service | Corrected operation files for all services |  | Team meeting -30 min , Client meeting - 60 mins ,Service operations modification - 1 hrs, Updating MOM - 15 mins | lunch and others 90mins, Softskill session - 2hr

## 23-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | web api(Department) |  |  | Meeting with Rafi-60mins,web api department-4hrs | Exploring Web api 1 hr,Break 40 mins
Gokul | Absent
Gokulraj | Layout for TMS | Footer, Head View pages(list of coordinator, trainer, trainee, reviewer) |  | Meeting with Rafi - 60mins, Working on Head Layout 120mins | Lunch and Tea break-75min
Iswarya | web API(Role) |  |  | 30 mins : Team meeting , 60 mins:Client meeting ,1hr : review the all Layout and clarifying the doubt | 30 mins : lunch and break time
Kavin | Layouts of TMS dashboard |  |  | Meeting with Rafi - 60mins, Working on layout for login and refining the training head-120mins | Lunch and Break-90 min,HTML exploration-60 min
Kirubaharan | Web API exploration ,Model for TMS |  |  | Meeting with Rafi - 1 hour, Web Api tutorial - 1 hour , Worked on namespace ,classes and properties-1hr | Lunch and break - 1 hour 30 mins
Prathima | exploration on web api,Creating Model for TMS |  |  | Review Meeting with Rafi-1hr web api (exploration)-2hr Creating Namespace ,classes and properties in VS code - 1hr | Lunch & Tea break - 1.5 hr
Ragu |  | profile page for training head and refining all layout |  | team discussion-20min,meeting with rafi-23min, team discussion-30min(abouth the layout completion) working on layout for profile view page (training head) -120min | lunch -1.15hrs
Sruthi | Absent
Sobhana | Absent
Arul | Department Service Api |  |  | Team meeting -30 min , Client meeting - 60 mins ,Updating MOM - 15min, Adding (Context,Controller,Httpverbs) in department service | lunch and breaks - 90mins,Design pattern - 55 mins,

## 25-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | web api(Department) |  |  | Team Meeting-30 mins,Meeting with Rafi-23mins,web api department-3hrs,total 3 hrs 53 mins | collecting System Issues in Corvus 40 mins,Exploring Web api 1 hr,Break 40 mins,relocating my system from caelum to corvus-40 mins,total 3 hrs
Gokul | Estimation web api | team meeting - 30 mins web api middleware exploration - 1 hr 30 mins meeting with rafi - 20 mins team meeting - 30 mins understanding EF ref code - 3 hr |  | 3hrs | 4hrs
Gokulraj | Layout for TMS | Filter, Search , Refining all pages and responsiveness |  | Team Discussion - 20mins, Meeting with Rafi - 20mins, Team Discussion about Layout Completion -30mins, alteration in signin, signup page | Lunch and Break-75 min
Iswarya | Home page Layout | Entire MOM Layout |  | 30 mins : Team meeting , 20 mins:Client meeting,30mins : Team discussion in Layout Completion, 1.30 mins MoM layout | 1.30 mins : lunch and break time
Kavin | Common Layout of TMS | Common login for TMS and refining the layout |  | Meeting with Rafi - 20mins, Team discussion-20 min,Working on Login layout-60 min,Team discussion-30 min | Lunch and Break-90 min
Kirubaharan | Working on Responsiveness for Create Topic page |  |  | Team meeting - 30 mins, Meeting with Rafi - 20 mins , Created a layout page (Create Topic and Assign course) - 2 hours | Others(Lunch and break) - 1 hour 30 mins, Tutorial about HTML - 1 hour
Prathima | exploration on web api | HTML layout for confirmation message box |  | Team meeting-20mins Review Meeting with Rafi-20mins team discussion -30 mins HTML layout (attendance,confirmation message box)-3.5hrs | Lunch & Tea break - 1.5 hr
Ragu |  | profile page for training head and refining all layout |  | team discussion-20min,meeting with rafi-23min, team discussion-30min(abouth the layout completion) working on layout for profile view page (training head) -120min | lunch -1.15hrs
Sruthi | Home Page Layout | layout for schedule review and view review for TMS |  | Team meeting for 30 mins , Client meeting- 20 mins, Team discussion for splitting the work - 30 mins, 1.30 mins for Review page | Lunch break - 1:30 mins
Sobhana |  | Trainee Feedback layout ,Course Feedback layout |  | Team meeting-20 mins, meeting with client -23 mins,Team meeting( About layout completion)-30 min, working on layout for trainee feedback and course feedback -3h30mins | Lunch -35mins,Break-20 min
Arul | Department Service Api |  |  | Team meeting -30 min , Client meeting - 20mins ,Updating MOM - 10min, Creating (CRUD operations) in department service - 4hrs | lunch and breaks - 90mins

## 26-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Arul | Web Api services | 8:30 - 9:05(35mins) : Updating timesheet and MOM, 9:05 - 9:30(25mins) : Team meeting, 9:30 - 10:20(50mins) : Softskill, 10:20 - 10:40(20mins) : break, 10:45 - 11:45(60mins) : Web api services added(User,Department,Role), 11:45 - 12:15(30mins) : Estimation of pages in TMS, 12:15 - 12:25(10mins) : Helping in resolve a conflict, 12:35 - 12:55(20mins) : Client meeting, 1:00 - 1:40(40mins) : Lunch, 2:00 - 2:40(40mins) : Web api session among team, 2:40 - 3:00(10mins) : worked on a Services, 3:00 - 3:40(40mins) : rework on a new repository, 3:40 - 4:15(35mins) : Implementing Serilog in api, 4:15 - 4:30(15mins) : break, 4:30 - 5:15(45mins) : Resolving conflict in webapi, 5:15 - 5:45(30mins) : Clarifying about repository and worked on new repository 7:00 - 7:45(45mis) : Midlleware exploration |  | 6.3 hrs | 3.10 hrs
Asuvath | web api Services and web api exploration |  |  | 20:00-21:00 : reviewing and understanding the Api services, 21:00-23:00 : Learning Angular<Components and lifecycle>, TOTAL-3 hrs | 8:00-17:00 : Went college for internals , TOTAL -9 hrs
Gokul | Web Api exploration, Ef Core exploration | 9:00 - 9:20 : TimeSheet, 9:20 - 9:35 : Team meeting, 9:35 - 10:20 : Softskill, 10:20 - 10:40 : Break, 10:40 - 10:55 : Estimation explaination, 10:55 - 11:45 : Web api services added(DbContext,Migrations,UserService), 11:45 - 12:35 : Estimation of pages in TMS, 12:35 - 12:56 : Client meeting, 12:56 - 1:30 : Lunch 1:30 - 2:00 : preparing for web api session 2:00 - 3:00 : worked on UserServices.cs, 3:00 - 4:00 : Web api session among team, 4:00 - 4:30 : worked on IRepository.cs, 4:30 - 4:45 : Break, 4:45 - 5:30 : Resolving conflict in Webapi |  | 4hrs | 4hrs
Gokulraj | Component in angular for common Layout pages | Layout for TMS |  | 8.40-9.00 : Updating Timesheet 9.05-9.30 : Team Discussion about work Progress 10.40-12.30 : Layout Integration and corrections in Layout 12.35-12.56 : Client(Rafi) Meeting 2.00-2.20 : Uploading Layout pages as static pages to Git publish 2.20-2.50 : Identify the Unique and Common Layout pages for Estimation 3.00-4.00 : Web Api Session amoung Team 4.30-4.50 : Presenting the Layout to the Client(Rafi) 4.50-5.00 : Discussion with Layout team about changes in Layout 5.00-5.40 : Discussion about Layout page Estimation | 9.30-10.20 : Softskill session 10.20-10.40 : Tea Break 1.00-2.00 : Lunch Break 4.00-4.30 : Tea Break
Iswarya |  | Estimation and Layout Correction |  | 8.45-9.00 : Updating Timesheet and HLD Document 9:05 - 9:30 : Team meeting 10:40-10:55 : Estimation explanation meeting 11:00-11:30 : Integrating my MOM layout with other layout pages 11.30-12.15: Helping in Attendence Layout 12:35 - 12:56 : meeting with Rafi 2.00-3.00 mins : Identifying the pages and Estimation 4.35-4.50 : Web API Session with other team 4.55-5.45: Layout Correction Explanation and Estimation | 9:30 - 10:20 : Softskill 3:00 - 4:00: webAPI Session with team 10:20 - 10:40 : break 1:00 - 1:40 : Lunch 4:00- 4:15 : break
Kavin | Component in angular for common Layout pages | Refining the layout and responvise |  | 8.45-9.05 : Updating Timesheet 9:05 - 9:30 : Team meeting 12:35 - 12:56 : meeting with Rafi 2.00-3.00 : Identifying the Unique page for Estimation 4.35-4.50 : Web API Session with team 4.55-5.30: Layout Correction Explanation and Estimation | 9.30-10.20 : Soft skill 10.30-11.45: prepare for internal review 1-1.45-Lunch 4.35-4.50 : Web API Session with other team 5.30-6: Internal Review with Anitha
Kirubaharan |  | Layout page for Assign course and Create topic |  | 9:20-9:30-Team meeting, 10:40-12:30:Worked on Layout page (Assign course and create topic), 12:35-12:55:Meeting with Rafi, 2:00-3:00: Web Api session among team, 4:30-5:30-Layout corrections and responsivenss | 9:30-10:20:Softskill session, 10:20-10:40:Break, 1:00-1:50:lunch break, 3:00-4:00:Explored about entity framework, 4:00-4:20:Tea break,
Prathima | exploration on web api | 8.45-9.00 : Updating Timesheet 9:05 - 9:30 : Team meeting 9:30 - 10:20 : Softskill session(Problem Solving) 10:20 - 10:40 : break 10:40-10:55 : Estimation explanation meeting 11.00-12.30: worked on attendace layout 12:35 - 12:56 : meeting with Rafi 1:00 - 1:40 : Lunch 2:00 - 3:00: webAPI Session with team members 3.00-3.40:exploration on html 3.40-4.00:uploading code in github 4:30- 4:45 : break 4.45-5.45:Exploration on web api 7.00-8.00:Brushing up of basic concepts in c# |  | 3 Hrs and 40 mins | 5 hrs and 10 mins
Ragu | creating component in angular | Layout for TMS |  | 8:50-9:00 : Updating Timesheet 9:05-9:30 : Team Discussion about work Progress 10:40-12:30 : intergarting the layout (TMS layout) 12:35-12:56 : Client(Rafi) Meeting 2:00-2:20 : creating the repositories and uploading the static page in github 2:20-2:50 : spliting the common page and prepaing for estimation 3:00-4:00 : Web Api Session amoung Team 4:30-4:50 : Presenting the Layout to the Client(Rafi) 4:50-5:00 : Discussion with Layout team about changes in Layout 5:00-5:40 : Discussion about Layout page Estimation 7:00-7:30 : correcting the changes in the layout | 9:30-10:20 : Softskill session 10:20-10:40 : Tea Break 1:00-2:00 : Lunch Break 4:00-4:30 : Tea Break
Sobhana | Exploration on web api | Layout for TMS |  | 8.45-9.00 : Updating Timesheet 9:00 - 9:30 : Team meeting 10:40-10:55 : Estimation explanation meeting 11:00-11:45 : Refining Feedback layout, intergrating with other layouts and updating in git 11.45-12.15 : Helping in Estimation 12:35 - 12:56: meeting with Rafi 2.00-3.00 : Identifying the pages and Estimation 3.00-4.00 : Web API Session with team 4.30-4.50 : Web API Session with other team 4.55- 5.45 : Exploring web api and installing packages ,Estimationing layout pages | 9:30 - 10:20 : Softskill 10.20 -10.40 : Break 1.00-1.40 : Lunch
Sruthi |  | Estimation for TMS and refineed layouts |  | 8.45-9.00 : Updating Timesheet and HLD Document 9:05 - 9:30 : Team meeting for work status 10:40-10:55 : Estimation explanation meeting with team 11:00-11:45 : Refining schedule review and review layout for TMS 11:45-12:30 : reviewing others layouts 12:35 - 12:56 : meeting with client 2:00-3:00 : Identifying the pages for Estimation 4.55-5.45: Layout Correction Explanation and Estimation | 9:30 - 10:20 : Softskill session 10:20 - 10:40 : break 1:00 - 1:40 : Lunch break 3:00 - 4:00: Web API Session with team members 4:00- 4:20 : break 4.35-4.50 : Entity framework Session with other team

## 27-04-22
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Arul | Timesheet and MOM updating | Project | 8:45 | 9:10 | 0:25 | Split | Time | Project
| Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Project | 3:30 | Non Project
| Api Service refining | Project | 10:35 | 11:45 | 1:10 | Non Project | 1:15 | Exploration
| Customer Meeting | Customer Review | 11:45 | 12:25 | 0:40 | Exploration | 1:30 | Meeting
| Learned Angular <Typescript Intorduction and Sample programs> | Exploration | 15:30 | 17:00 | 1:30 | Meeting | 0:45 | Customer Review
| Api Service implementation on Controller | Project | 15:15 | 16:30 | 1:15 | Customer Review | 0:40 | Lunch and Break
| Service explanation to Members | Non Project | 14:00 | 15:15 | 1:15 | Lunch and Break | 0:55
| Lunch | Lunch and Break | 13:00 | 13:40 | 0:40 | TOTAL | 8:35
| Morning Break | Lunch and Break | 10:20 | 10:30 | 0:10
| Evening Break | Lunch and Break | 16:45 | 16:50 | 0:05
| Api Swagger Testing | Project | 17:00 | 17:40 | 0:40
0:00
0:00
0:00
0:00
Asuvath | Went to College for internal exams | Non Project | 9:00 | 425:00 | 416:00 | Split | Time
| understanding and reviewing API services | Project | 20:00 | 525:00 | 505:00 | Project | 507:00
| Learned Angular <Components and life cycle> | Project | 525:00 | 527:00 | 2:00 | Non Project | 416:00
[5 empty] | 0:00 | Exploration | 0:00
[5 empty] | 0:00 | Meeting | 0:00
[5 empty] | 0:00 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 0:00
[5 empty] | 0:00 | TOTAL | 923:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
Gokul | Time Sheet | Non Project | 9:00 | 9:20 | 0:20 | Split | Time
| Database Migration | Project | 9:20 | 9:50 | 0:30 | Project | 3:05
| Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Non Project | 0:34
| Logging in user services & user controller | Project | 10:35 | 10:50 | 0:15 | Exploration | 2:15
| User Services List of Users by Role | Project | 10:50 | 11:20 | 0:30 | Meeting | 0:45
| Morning Break | Lunch and Break | 11:20 | 11:45 | 0:25 | Customer Review | 0:34
| client meeting | Customer Review | 11:48 | 12:22 | 0:34 | Lunch and Break | 1:12
| helping other team with ui | Non Project | 12:26 | 12:40 | 0:14 | TOTAL | 8:25
| fixing errors in user services | Project | 12:40 | 13:00 | 0:20
| ef core exploration | Exploration | 17:00 | 17:45 | 0:45
| Lunch | Lunch and Break | 13:00 | 13:47 | 0:47
| CRUD Operation in user Services | Project | 13:50 | 15:20 | 1:30
| Technical Session | Exploration | 15:30 | 17:00 | 1:30
0:00
Gokulraj | Time Sheet Updating | Non Project | 9:00 | 9:30 | 0:30 | Split | Time
| Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Project | 315:35
| Estimation for Dashboard | Project | 11:20 | 11:40 | 0:20 | Non Project | 0:38
| Customer Meeting | Customer Review | 11:45 | 12:25 | 0:40 | Exploration | 1:30
| Lunch | Lunch and Break | 13:00 | 14:00 | 1:00 | Meeting | 0:45
| Morning Break | Lunch and Break | 10:35 | 11:00 | 0:25 | Customer Review | 0:40
| Evening Break | Lunch and Break | 15:15 | 15:30 | 0:15 | Lunch and Break | 1:40
| Learned Angular <Typescript Introduction and Installation> | Exploration | 15:30 | 17:00 | 1:30 | TOTAL | 320:48
| Discussion about Services with Arul and Spliting Services | Project | 14:00 | 15:15 | 1:15
| Service-Review | Project | 21:00 | 22:00 | 1:00
| Web API User Service Exploration with Gokul | Project | 12:30 | 325:00 | 312:30
| Discussion about Timesheet and Team performance Index with Rafi | Non Project | 11:12 | 11:20 | 0:08
| Estimation Discussion | Project | 17:00 | 17:30 | 0:30
0:00
0:00
Iswarya | Updating TimeSheet | Non Project | 8:30 | 9:00 | 0:30 | Split | Time
| Working on HTML layout | Project | 9:10 | 9:40 | 0:30 | Project | 2:25
| Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Non Project | 0:30
| Morning Break | Lunch and Break | 10:40 | 10:55 | 0:15 | Exploration | 73:30
| Estimation Preparation | Project | 11:05 | 11:20 | 0:15 | Meeting | 0:45
| Customer Meeting | Customer Review | 11:48 | 12:22 | 0:34 | Customer Review | 0:34
| Web API Exploration (user services) with gokul | Project | 12:30 | 13:00 | 0:30 | Lunch and Break | 1:30
| Lunch | Lunch and Break | 13:00 | 14:00 | 1:00 | TOTAL | 79:14
| Working on Feedback services | Project | 2:10 | 3:20 | 1:10
| Learned Angular <TypeScript Introduction and Simple Examples> | Exploration | 15:30 | 89:00 | 73:30
| Evening Break | Lunch and Break | 17:10 | 17:25 | 0:15
| Estimation Discussion | Project | 17:25 | 17:45 | 0:20
Kavin | Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 3:07
| Customer Meeting | Project | 11:48 | 12:25 | 0:37 | Non Project | 0:28
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Exploration | 1:32
| Lunch | Lunch and Break | 12:45 | 13:30 | 0:45 | Meeting | 0:45
| Morning Break | Lunch and Break | 10:40 | 11:00 | 0:20 | Customer Review | 0:00
| Evening Break | Lunch and Break | 15:15 | 15:30 | 0:15 | Lunch and Break | 1:20
| Learned Angular <Introduction of Typescript , VS code Installation> | Exploration | 15:30 | 17:02 | 1:32 | TOTAL | 7:12
| Time Sheet | Non Project | 8:50 | 9:10 | 0:20
| Service Discussion with Arul and Spliting the Service | Project | 14:00 | 15:15 | 1:15
| Service-Course | Project | 21:00 | 22:15 | 1:15
| Discussion about New Timesheet And Team Performance | Non Project | 11:12 | 11:20 | 0:08
0:00
0:00
0:00
Kirubaharan | Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Split | Time
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Project | 1:35
| Customer Meeting | Customer Review | 11:48 | 12:22 | 0:34 | Non Project | 4:15
| Soft Skill | Non Project | 0:00 | 0:00 | 0:00 | Exploration | 0:00
| Lunch | Lunch and Break | 13:10 | 13:50 | 0:40 | Meeting | 0:45
| Morning Break | Lunch and Break | 10:45 | 11:00 | 0:15 | Customer Review | 0:34
| Evening Break | Lunch and Break | 0:00 | 0:00 | 0:00 | Lunch and Break | 0:55
| Prepared for Internal Review | Non Project | 10:00 | 10:45 | 0:45 | TOTAL | 8:04
| Session about Serivces | Project | 14:00 | 15:15 | 1:15
| Updating TimeSheet | Project | 9:00 | 9:20 | 0:20
| Technical Session | Non Project | 15:30 | 17:00 | 1:30
| Prepared for Internal review | Non Project | 20:00 | 22:00 | 2:00
0:00
0:00
0:00
Prathima | Updating TimeSheet | Project | 9:00 | 9:15 | 0:15 | Split | Time
| Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Project | 3:20
| Morning Break | Lunch and Break | 10:40 | 10:55 | 0:15 | Non Project | 0:00
| Customer Meeting | Customer Review | 11:48 | 12:22 | 0:34 | Exploration | 1:30
| Lunch | Lunch and Break | 13:00 | 13:45 | 0:45 | Meeting | 0:45
| Working on WebAPI (Review services) | Project | 13:50 | 15:30 | 1:40 | Customer Review | 0:34
| Learned Angular <data type,variable,type script > | Exploration | 15:30 | 17:00 | 1:30 | Lunch and Break | 1:15
| evening Break | Lunch and Break | 17:00 | 17:15 | 0:15 | TOTAL | 7:24
| Understanding the Department,User Services | Project | 12:30 | 13:00 | 0:30
| Estimation for Coordinator list page | Project | 11:00 | 11:30 | 0:30
| Reworking on model(review service) | Project | 17:20 | 17:45 | 0:25
0:00
0:00
0:00
0:00
Ragu | Timesheet Updating | Non Project | 9:00 | 9:20 | 0:20 | Split | Time
| Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Project | 3:40
| Estimation for ProfileView | Project | 11:20 | 11:45 | 0:25 | Non Project | 0:28
| Customer Meeting | Customer Review | 11:45 | 12:25 | 0:40 | Exploration | 1:30
| Lunch | Lunch and Break | 13:00 | 13:40 | 0:40 | Meeting | 0:45
| Morning Break | Lunch and Break | 10:35 | 11:00 | 0:25 | Customer Review | 0:40
| Evening Break | Lunch and Break | 15:15 | 15:30 | 0:15 | Lunch and Break | 1:20
| Learned Angular <Typescript introduction> | Exploration | 15:30 | 17:00 | 1:30 | TOTAL | 8:23
| discussion on services and spliting the services | Project | 14:00 | 15:15 | 1:15
| Service-Role | Project | 21:00 | 22:00 | 1:00
| Estimation for unique pages | Project | 17:00 | 17:30 | 0:30
| Web API Exploration (user services) with gokul | Project | 12:30 | 13:00 | 0:30
| discussion about the rank table | Non Project | 11:12 | 11:20 | 0:08
0:00
0:00
Sobhana | Timesheet | Project | 9:00 | 9:20 | 0:20 | Split | Time
| Working on HTML layout (Refining) | Project | 9:20 | 9:50 | 0:30 | Project | 3:35
| Team Meeting | Meeting | 9:50 | 10:35 | 0:45 | Non Project | 0:00
| Estimation for department page | Project | 11:00 | 11:30 | 0:30 | Exploration | 2:00
| Customer Review | Customer Review | 11:45 | 12:25 | 0:40 | Meeting | 0:45
| Web API Exploration (user services) with gokul | Project | 12:25 | 13:00 | 0:35 | Customer Review | 0:40
| Discussion on services and spliting the services | Project | 13:45 | 14:40 | 0:55 | Lunch and Break | 1:25
| Angular session <Typescript introduction> | Exploration | 15:00 | 17:00 | 2:00 | TOTAL | 8:25
| Pulling from git (Web API), Exploring and working on department services | Project | 17:00 | 17:45 | 0:45
0:00
| Lunch | Lunch and Break | 1:00 | 1:45 | 0:45
| Morning Break | Lunch and Break | 10:40 | 11:00 | 0:20
| Evening Break | Lunch and Break | 2:40 | 3:00 | 0:20
0:00
0:00
Sruthi | Team Meeting | Project | 10:00 | 10:10 | 0:10 | Split | Time
| Soft Skill | Non Project | 10:15 | 11:00 | 0:45 | Project | 5:45
| Customer Meeting | Project | 11:45 | 12:20 | 0:35 | Non Project | 1:45
| Soft Skill | Non Project | 11:30 | 12:30 | 1:00 | Exploration | 0:00
| Lunch | Lunch and Break | 13:00 | 13:40 | 0:40 | Meeting | 0:00
| Morning Break | Lunch and Break | 11:20 | 11:30 | 0:10 | Customer Review | 0:00
| Evening Break | Lunch and Break | 15:45 | 16:00 | 0:15 | Lunch and Break | 1:05
| Learned Angular <Topics> | Project | 16:00 | 18:00 | 2:00 | TOTAL | 8:35
| Working on HTML layout | Project | 18:00 | 21:00 | 3:00
0:00
0:00
0:00
0:00
0:00
0:00