## Sheet1
S.No | Task | Sub Tasks | Estimation in Hrs | Code Merging
1 | Login page | Low Level Design - Sequence Diagram | 4 | Integration Testing
|  | HTML preparation | 2 | Compatibility testing
|  | HTML Validations | 1 | Deployment Documentation
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
2 | Home page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
3 | Profile page | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
4 | List page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
5 | Add course | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
6 | Edit course | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
7 | Add topic | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
8 | Edit topic | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
9 | Assign course | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
10 | Schedule Review | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
11 | View Review | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
12 | Add MOM | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
13 | Edit MOM | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
14 | View MOM | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
15 | View course | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
16 | View topic | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
17 | Add Attendance | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
18 | View Attendance | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
19 | Add assignment | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
20 | Edit assignment | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
21 | View topic assignment | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
22 | Add Course Feedback | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
23 | Edit Course Feedback | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
24 | View Course Feedback | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
25 | Add Trainee Feedback | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
26 | Edit Trainee Feedback | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
27 | View Trianee Feedback | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
28 | View Course Feedback | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
29 | Dashboard | Low Level Design - Sequence Diagram | 4 | Code Merging
|  | HTML preparation | 2 | Integration Testing
|  | HTML Validations | 1 | Compatibility testing
|  | Web API Integration | 2 | Deployment Documentation
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
30 | Popup | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 2
|  | Web API - Service Implementation | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
14.5
|  | Total esimated time for Unique pages | 733.5

## refined Estimation
S.No | Task | Sub Tasks | Estimation in Hrs
1 | Login page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
|  | Total Time | 22.5
2 | Home page | Low Level Design - Sequence Diagram | 0
|  | HTML preparation | 1
|  | HTML Validations | 0
|  | Web API Integration | 0
|  | Web API - Service Implementation | 0
|  | Swagger - API Documentation | 0
|  | Service Validations , Exception and Logging | 0
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
Unit Testing
Integration Testing
2
3 | Dashboard | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 4
Web API - Service Implementation
|  | Get user(id) | 0.5
|  | count (Department) | 2
|  | count(trainer) | 2
|  | count(tarinee) | 2
|  | count(co ordinator) | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
27
4 | Profile Page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | Get user(id) | 1.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
5 | List(Coordinator) | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | getall(role ID) | 2
|  | search(user) | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
23
6 | Add(coordinator) | Low Level Design - Sequence Diagram | 2.5
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 4
Web API - Service Implementation
|  | create(co-ordinator) | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
23.5
7 | Edit(coordinator) | Low Level Design - Sequence Diagram | 2.5
|  | HTML preparation | 1
|  | HTML Validations | 2
|  | Web API Integration | 4
Web API - Service Implementation
|  | update(co-ordinator) | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20.5
8 | Disable(coordinator) | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | delete(co-ordinator) | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
9 | List view(dept) | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | getall(dept) | 2
|  | search(dept) | 1
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
10 | Add dept | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1.5
|  | HTML Validations | 1.5
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | create(dept) | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
23
11 | Edit dept | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | Swagger - API Documentation | 2
|  | update(dept) | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
18
12 | Delete dept | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | delete(dept) | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
18
13 | Add Topic | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1.5
|  | HTML Validations | 1.5
|  | Web API Integration | 4
Web API - Service Implementation
|  | create(topic) | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
14 | Edit Topic | Low Level Design - Sequence Diagram | 2.5
|  | HTML preparation | 1
|  | HTML Validations | 1.5
|  | Web API Integration | 4
Web API - Service Implementation
|  | update(topic) | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
15 | Add Course | Low Level Design - Sequence Diagram | 3
|  | HTML preparation | 1
|  | HTML Validations | 1.5
|  | Web API Integration | 4
Web API - Service Implementation
|  | create(course) | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19.5
16 | Edit Course | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1.5
|  | HTML Validations | 1.5
|  | Web API Integration | 4
Web API - Service Implementation
|  | update(course) | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
17 | Delete Course | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | delete(course) | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
18
18 | View Attendance | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2.5
|  | HTML Validations | 1.5
|  | Web API Integration | 4
Web API - Service Implementation
|  | getallusercourse() | 1
|  | getattendance(topic) | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
Unit Testing
|  | Integration Testing | 2
22
19 | Assign Course | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | getalluser(deptID) | 2
|  | getallcourse(deptID) | 2
getalldept()
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
20 | Schedule Review | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | getalluser(roleID) | 2
|  | createreview() | 2
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
21 | Edit assigned review | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | updatereview() | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
22 | Cancel review | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
deletereview()
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
23 | My Course list | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | getallcourse(userID) | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
24 | Course detail view | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 2
Web API - Service Implementation
|  | viewcourse(courseID) | 3
|  | Swagger - API Documentation | 4
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
25 | Topic detail view | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
viewcourse(topicID)
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
26 | Add assignment | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | createassignmet() | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
27 | Edit assignment | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | updateassignment() | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
28 | Delete assignment | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | deleteassignment() | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
29 | Add feedback | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | createfeedback() | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
30 | View feedback | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
Web API - Service Implementation
|  | viewfeedback() | 3
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
19
sum |  |  | 565
31 | Edit feedback | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
32 | Review details | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
33 | Add MOM | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
34 | View MOM | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
35 | Assignment status view | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20
36 | View assignment | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
Integration Testing
20

## Estimation SprintOne
S.No | Task | Sub Tasks | Estimation in Hrs
1 | Login page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 3
|  | HTML Validations | 2
|  | Web API Integration | 3
|  | Web API - Service Implementation | 3
|  | Swagger - API Documentation | 1.5
|  | Service Validations , Exception and Logging | 1.5
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
|  | Total Time | 18.5
2 | Dashboard | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 6
|  | Web API - Service Implementation | 7.5
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
Code Review
Unit Testing
Integration Testing
|  | Total Time | 25.5
3 | View Profile | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 6
|  | Web API - Service Implementation | 7
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
Code Review
Unit Testing
Integration Testing
|  | Total Time | 25
4 | coordinator list | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 1
|  | HTML Validations | 1.5
|  | Web API Integration | 6
|  | Web API - Service Implementation | 7
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
|  | Total Time | 26
5 | Coordinator(Add,Edit) | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API Integration | 3
|  | Web API - Service Implementation | 5
|  | Swagger - API Documentation | 2.5
|  | Service Validations , Exception and Logging | 3.5
|  | Code Cleanup | 0.5
|  | Code Review | 2
|  | Unit Testing | 1
|  | Integration Testing | 1.5
|  | Total Time | 23
6 | Dept(ADD,EDIT,DEL) | Low Level Design - Sequence Diagram | 3.5
|  | HTML preparation | 3
|  | HTML Validations | 1
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 0.5
Code Review
Unit Testing
Integration Testing
|  | Total Time | 22
7 | Course(ADD,EDIT) | Low Level Design - Sequence Diagram | 3
|  | HTML preparation | 4
|  | HTML Validations | 2.5
|  | Web API Integration | 4.5
|  | Web API - Service Implementation | 5
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 1
Code Review
Unit Testing
Integration Testing
|  | Total Time | 26
8 | Course List | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 1.5
|  | HTML Validations | 2
|  | Web API Integration | 3
|  | Web API - Service Implementation | 5
|  | Swagger - API Documentation | 3
|  | Service Validations , Exception and Logging | 4
|  | Code Cleanup | 1
Code Review
Unit Testing
Integration Testing
|  | Total Time | 23.5
9 | View Attendence | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 1.5
|  | HTML Validations | 1.5
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
Code Review
Unit Testing
Integration Testing
|  | Total Time | 21
10 | Course Feedback | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 1.5
|  | Web API Integration | 4
|  | Web API - Service Implementation | 4.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2.5
|  | Code Cleanup | 1
Code Review
Unit Testing
Integration Testing
|  | Total Time | 20.5
11 | MOM | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 2
|  | HTML Validations | 2
|  | Web API Integration | 5.5
|  | Web API - Service Implementation | 7
|  | Swagger - API Documentation | 1.5
|  | Service Validations , Exception and Logging | 3
|  | Code Cleanup | 1
Code Review
Unit Testing
Integration Testing
|  | Total Time | 26
|  | Total time | 252.5