## 5-4-22
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Sharing the points on Individual User Story,Refining the Workflow | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Gokul | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Gokulraj | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Iswarya | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Kavin | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Kirubaharan | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Prathima | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Ragu | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Sruthi | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Sobhana | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30

## 6-4-22
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Discussion About User Stories And User Flow.Session With Rafi.Started Designing UI,Discussion About Estimation | Prototype,Constraints,Assumption | Acceptance criteria | 6:30 | 1:00
Gokul | trainee flow mockups, prototypes | landing page, dashboard page, courses page,attendance page, feedback page |  | rafi meeting - 1hr, team meeting - 2hr, UI templates - 2hr, total time - 5hr | figma - 1hr 30 mins, lunch & tea break - 1 hr 15 mins, total time - 2 hr15 mins
Gokulraj | Working on Constraints, Assumptions. | Discuss with Rafi about Userstory, Correction in Userstory, Discussion about Prototype, Working on Acceptance Cretiria. |  | Rafi Meeting - 1hour, Userstory - 15min, Team Disscussion - 2 hours, Prototype - 2.5 hours, Acceptance Criteria - 30min. Toatal 6.15 Hours | Figma tutorial - 30min
Iswarya | Acceptance criteria | Discussion with rafi about user story and user flow,Team discussion about prototype,UI designing. |  | 5:30 | 2:30
Kavin | Working on UI designing ,Acceptance criteria | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story |  | rafi meeting - 1hr, team meeting - 2hr, UI templates,acceptance certeria - 2.5hr, total time - 5.30hr | 2:30
Kirubaharan | Working on Acceptance criteria,constraints and Assumption | Meeting with client about user story and userflow,Team discussion about prototype | Acceptance criteria | 5:30 | 2:30
Prathima | Working on UI designing ,Acceptance criteria | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story,user flow |  | rafi meeting - 1hr, team meeting - 2hr, UI templates,acceptance certeria - 2.5hr, total time - 5.30hr | 2:30
Ragu | working on constraints, assumptions. | Discuss with Rafi about user story, correction in user story, discussion about prototype, working on acceptance cretiria. |  | Rafi Meeting - 1hour, Userstory - 15min, Team Disscussion - 2 hours, Prototype - 2.5 hours, Acceptance Criteria - 30min. Toatal 6.15 Hours | Figma tutorial - 30min
Sruthi | Acceptance criteria | Discussion with rafi about user story and user flow,Team discussion about prototype,UI designing. |  | 5:30 | 2:30
Sobhana | Working on UI designing ,Acceptance criteria,constraints | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story,user flow |  | rafi meeting - 1hr, team meeting - 2hr, UI templates - 2hr,constraints and acceptance criteria-30 min, total time - 5.30hr | 2:30
Arul | Understanding existing work done by team members

## 7-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Landing page(Trainer) | Trainer Pages( My course , Topics,Assignments,Feedback) |  | Assumption and Constraints -50mis,Meeting With rafi-45 mins,Team Discussion-50 mins,Creating UI Templates -2:15 hrs ,Total Time-4:40hrs | Session With Rafi(Builder Pattern)-30mins,Softskill Session-45 mins,others 20mins,Abstract Design Pattern-40mins ,Non Project-2:15 hrs
Gokul | prototype for trainee | Trainee requirements refining ,designed 8 pages for trainee, |  | Meeting With rafi - 45 mins,Team Discussion - 50 mins,created trainee pages - 3:00 hrs ,Total Time - 4:45 | abstratct pattern - 45 mins, lunch - 45 mins, break - 30 mins, total time -2 hrs
Gokulraj |  | Training Head - Acceptance Cretiria, Constraints, Assumptions. | Previous UI design has been discarded | Meeting with Client Rafi(About UI design)-45min, Team Discussin about UI design-60min, Making changes in Training Haed Acceptance Cretiria, Constraints, Assumptions-90min,Discussion with Teammate about Acceptance Cretiria, Constraints, Assumptions and UI design(Training Head)-60min. | Abstract Pattern Session-40min, others(lunch & tea break)-90min
Iswarya |  | UI designing on trainer - landing page,feedback page | Previous UI design has been discarded | Worked on acceptance criteria and UI design - 1:30 mins,Prototype disscussion with rafi - 45 mins,team discussion about modification on prototype - 50 mins, Trainer Landpage,feedback page-1 hr | Abstract Pattern-40 mins,Softskill Session-45 mins,
Kavin | UI design (dashboard )for training co ordinator | UI design for training Co-Ordinator | Previous UI design has been refined | Meeting with rafi (reviewed UI design )-1hr Discussion with team about UI design-1hr UI design for training Co-Ordinator-2hrs Discussion with Prathima for UI design for training Co Ordinator-1hr | Abstract Pattern Session-40min lunch,break-1.30hr
Kirubaharan |  | Assumption, Acceptance Criteria and constraints for Trainee stories | Prototype design | Discussion with team members about UI prototype - 40 mins, Worked on Acceptance criteria ,assumption and constraints for Trainee - 2 hours,Meeting with Rafi - 1 hour, | Design pattern session - 40 mins ,softskill session- 50 mins,Others - 1 hour 20 mins
Prathima | UI design (dashboard )for training co ordinator | Meeting with rafi (reviewed UI design ),acceptance criteria,containts,assumption for training co ordinator |  | Meeting with rafi (reviewed UI design )-1hr Discussion with team about UI design-1hr Completed acceptance criteria,assumption,Contraints for training co-ordination user stories.-2hrs Discussion with Kavin for UI design for training Co Ordinator-1hr | Abstract Pattern Session-40min lunch,break-1.30hr
Ragu | Landing page(Co ordinator) | Training head - UI designing ( Login page,dashboard,register page, View status page, Filter page) | Previous UI design has been discarded | Meeting with Rafi( about UI designing)- 45min, team discussion about UI designing -1hr, completed UI design for training head(Login page,dashboard,register page, View status page, Filter page)-3hrs discussion with teamate about acceptance criteria and constraints fro training head - 1hr. | Abstract pattern session - 40min lunch and break 1.30hrs
Sruthi |  | Trainer - constraints, acceptance criteria, assumptions | Previous trainer UI design has been discarded | Worked on acceptance criteria and UI design - 1:30 mins,Prototype disscussion with rafi - 45 mins,team discussion about modification on prototype - 50 mins, Trainer - constraints, acceptance criteria, assumptions - 1 hr | Session with Rafi about abstract pattern - 40 mins
Sobhana | UI design (dashboard )for training co ordinator | Meeting with rafi (reviewed UI design ),acceptance criteria,containts,assumption for training co ordinator,Refining UI for co-ordinator | Previous UI design has been discarded | Meeting with client-1hr Discussion with team about UI design-1hr acceptance criteria,assumption,Contraints for training co-ordinater for user stories.-1.30hrs UI design for training Co Ordinator-1.30hr | abstract pattern - 45 mins, lunch - 45 mins, break - 20 mins
Arul | Refining trainee user stories | Assumption, Acceptance Criteria and constraints for Trainee stories | Prototype design | Meeting with client - 45mins,I've discussed about UI protyping with team members - 45mins, Done acceptance criteria for Trainee user stories - 120 mins | Softskill Session-45 mins, Design pattern session ,others 90mins

## 8-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Trainer | Co-Ordinator(Schedule Review,attendance,Course flow),Trainee(Feedback,Assignment,Mom) |  | Workflow Integration-1 hr,Reviewing-1 hr,Meeting With Rafi-1:40 hrs,Worked On Ui For Co-ordinator-2 hrs,ui Trainer-1 hr,Total Time-6:40 hrs | Break-1 hr
Gokul | ABSENT | ABSENT |  | ABSENT | ABSENT
Gokulraj | Designing prototype | Entities and Data Model Rough |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design and Entity - 120mins, Correction in Design - 60mins | Builder Pattern Session-60min, Photo Shoot at BasketBall court - 60 mins, others(lunch & tea break)-90min
Iswarya |  | Trainer course,topic,assignment,list of trinee and their detail page UI Design |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design and Entity - 120mins, Correction in Design - 60mins
Kavin | UI design for training co ordinator and Training head refining | Training head login,register,Dashboard and List of department |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design-120 min, Training head Design - 60mins and Prepare for presentation in Adaptor pattern-60 mina | Pattern Session-60min, Photo Shoot at Volleyball court - 60 mins, others(lunch & tea break)-1.15hour
Kirubaharan |  | Trainee acceptance criteria, Constraints and assumption |  | Meeting with Rafi -50 mins,Corrections in Design - 60 mins,Team discussion about entity and design -180 mins | Builder pattern session-60 mins,Friday activities-60 mins, Others - 90 mins
Prathima | UI design (dashboard )for training co ordinator,entity framework and requirements | UI for trainee |  | Meeting with Rafi -1hr(reviewed UI Design)Corrections in Design - 1hr,Team discussion about entity and design -2hrs | Builder Design Pattern and prototype Session-1hr, Photo Shoot at basketball court - 1hr, others(lunch & tea break)-1.30hr
Ragu | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sruthi |  | ABSENT | ABSENT | ABSENT | ABSENT
Sobhana | UI design (dashboard )for training co- ordinator | UI for training coordinator | Previous UI design has been discarded | Meeting with Rafi -1hr,Corrections in Design - 1hr,Team discussion about entity and design -3hrs | Builder Design Pattern and prototype Session-1hr, Photo Shoot at basketball court - 1hr, others(lunch & tea break)-1.30hr ,review-45min
Arul | Designing prototype | Entities and Data model | Exploration | Meeting with client - 45mins,I've discussed about User flow team members - 120mins, Done entity model rough - 60 mins | Softskill -45 mins, Design pattern session ,others 90mins

## 9-4-22
- | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Entity ,Attributes | Training Co-ordinator(Review,Assignment),Consistent check in Training Co-ordinator |  | Team discussion - UI Integration -45 mins, Refining Flow Correction 2 hrs,Consistent Check-2hrs,ui design(Co-ordinator,Trainee) 2 hrs,Meeting With Rafi-1:45 hrs.Total 8:45 hrs | Break-1:00 hr
Gokul | ABSENT | ABSENT |  | ABSENT
Gokulraj | Training head and training co-ordinator refining | Training Head UI page |  | Team meeting -60mins ,Correction in UI design-2hrs, entity frame work and datamodel -90 min ,Meeting with Rafi -1.45hours(reviewed UI Design) | others(lunch & tea break)-90min
Iswarya | Data Model | Trainer course,topic,assignment,list of trinee and their detail page UI Design |  | Training co-ordinator UI Discussion-1.30 hrs and design-3hrs,Meeting with Rafi -1.30 hrs. Sunday Trainer UI correction and Design-3hrs
Kavin | UI design for training co ordinator (Assign course,review ,and attendance) | Ui design Training Co-ordinator Dashboard and create course ,assign courseand prepare for presentation in design pattern |  | Prepare for presentation in design pattern -90 min ,Meeting with client (Rafi) - 1.45hours,Team meeting -60mins | Others(lunch & tea break)-1.30hour
Kirubaharan |  | Consistency checking in Trainee, Entity modeling |  | Team discussion about UI integration - 45 mins , Entity modelling - 1 hour,consistency checking - 2 hours,review with Rafi - 100 mins | Lunch and other breaks - 1 hour 30 mins
Prathima | Entity ,Attributes | UI design for training co ordintor(schedule review),dashboard for training co-cordinator,trainee,trainer,training head, Entity framework and data model |  | Team meeting -60mins ,Correction in UI design-2hrs, entity frame work and datamodel -90 min ,Meeting with Rafi -1.45hours(reviewed UI Design) | others(lunch & tea break)-1.30hr
Ragu | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sruthi | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sobhana | UI design (dashboard )for training co- ordinator | UI for trainee and trainer |  | Group discussion about UI integration - 45 mins , Entity modelling - 1 hour,Consistency checking - 2 hours,Meeting with rafi - 1.45 mins | Lunch : 1hour, Break:20 mins
Arul |  | Entities and Data model |  | Group discussion about UI integration - 45 mins , Entity modelling - 1 hour,Consistency checking - 2 hours,Session with Rafi - 100 mins | Break-2:00 hr

## 11-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Trainer UI | Co-Ordinator(Schedule Review,attendance,Course flow),Trainee(Feedback,Assignment,Mom) |  | Workflow Integration-1 hr,Reviewing-1 hr,Meeting With Rafi-1:40 hrs,Worked On Ui For Co-ordinator-2 hrs,ui Trainer-1 hr,Total Time-6:40 hrs | Break-1 hr
Gokul | Entity relationships, Entity attributes | Completed Changes in Trainee Design, Completed changes in Trainer Design, Worked on Data Models in TMS |  | Changes in Trainee Design - 2hr,Meeting With Rafi - 1hr 30 mins, Data Models - 1hr 30 mins total hrs- 5hrs | Lunch and break 1hr 15 mins, self exploration - entity frame work - 1hr total hrs - 2 hrs 15 mins
Gokulraj | Entity, Date model and relationships | Training Head and Co-ordinator Dessign flow |  | Team Disscussion 20 mins about design flow, Worked on Training Head and co-ordinator design flow 120 mins, Meeting with client (Rafi) - 90mins, Team Discussion about Design and Entity - 20mins, Alteration in Head and Co-ordinator Design flow - 120mins | Lunch and Tea break-90min
Iswarya | Data model Relationship | Entities and Data Model Rough |  | Team discussion-15 mins,working with Data model-2hrs, Meeting with client (Rafi) - 1.30 hrs | Preparing for review-2.30hrs, Attending Review-50 mins
Kavin | UI design for training co ordinator and Trainee consistency and naming conversion | Training head login,register,Dashboard and List of department |  | Meeting with Rafi-100 minutes,Worked on Training Head naming conversion and consistency-2 hours ,Discussion with team - 20 mins | others(lunch & tea break)-1.30hour
Kirubaharan | Redifining the acceptance criteria | Reviewed acceptance criteria for Trainee ,Trainer,training coordinator,Training head, Updated MOM, Entering data in entity model |  | Discussion with team - 20 mins, Worked on entity data model for trainee and collaborated with others-120 mins,meeting with Rafi- 100 mins | Prepared for code review - 1 hour , others - 90 mins
Prathima | Entity data model operation for Trainer | Entity datamodel ,artributes,relationship for trainer |  | Discussion with team - 20 mins, Worked on entity data model for trainer -3 hours ,meeting with Rafi- 100 mins | others(lunch & tea break)-1.30hour
Ragu | Entity data model | entered sample data for head , co ordinator, trainee , trainer. |  | discussion with team -20min, reviewed the head and co ordinator UI, meeting rafi 100 mins , entering sample data for head,co ordinator, trainer , trainee - 3 hrs, editing the changes in UI ( head , co ordinator, trainer, trainee). | lunch and break 1.30hrs
Sruthi | Data model Relationship | Entities and attributes for all users |  | Team discussion-15 mins,working with Data model-2hrs, Meeting with client (Rafi) - 1.30 hrs,Prepared data model for all users - 3 hrs | Break - 1 hr
Sobhana | Entity Data model and its Relationship | Entity datamodel for all users |  | Discussion with team -20min,meeting rafi -1.30hours , Entity data model for trainee and integrated with others-3.30 hours | Lunch -45mins,Break-20 min
Arul | Redifining the acceptance criteria | Reviewed acceptance criteria for Trainee, Trainer, Training co ordinator, Trainnig Head, Entering data in entity model | Exploration | Meeting with client - 90 mins, Discussion with team - 10mins. I've decided to work on entity data model data entry - 120mins and reviewing UI flow | lunch and others 130mins

## 12-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Data model (Behaviours) | UI(Trainer) |  | Team,Discussion 30mins,iUI(Trainer)-2hrs,Meeting With Rafi-1 hr-total -3:30 hrs | session with anitha(1hr),Preaparation for Presentation-3hrs,Total-4 hrs
Gokul |  | team meeting - 30 mins,TMS data model refining - 2 hr 30 mins, Data entry in TMS - 30 mins, TMS relation ship mapping - 30 mins, rafi meeting - 1hr, MOM - 30 mins |  | 4hrs 30 mins | Lunch & break - 1hr 30 mins,teaching others - 1hr
Gokulraj | Date model, relationships and behaviour | TMS Full UI Design Flow |  | Team Disscussion 30 mins about Design Integration and Data Model, Integration on Training Head, Co-ordinator, Trainer, Trainee design flow 100 mins, Meeting with client (Rafi) - 60mins, Creating Reviewer Flow and Making Changes in Course Flow 60mins, Finalize the TMS Design Flow 120mins | Lunch and Tea break-90min
Iswarya | Class model with operations | Data models entities and attributes |  | Team meeting - 30 mins, Refining Entities and attributes for TMS - 2 hr 30 mins, rafi meeting - 1hr, MOM - 30 mins | Session with Anitha-1 hr, worked with assignments given by anitha, Break - 1:30 hrs
Kavin | Entity Date Model and Relationships | UI design Consistency for Trainee and trainer |  | Meeting with Rafi-60 minutes,Worked on Trainer, and Trainee naming conversion and consistency-2 hours ,Discussion with team - 30mins | others(lunch & tea break)-100 min
Kirubaharan | Behaviours of entity and view models | Data models entities and attributes |  | Discussion with team - 20 mins, meeting with 60 mins , Prepared MOM | Session with Anitha - 1 hour, prepared for presentation - 2 hours,Others- 1 hour 30 mins
Prathima | Entity data model operation for Trainer | Entity datamodel ,artributes for trainer |  | Team meeting - 30 mins, Refining Entities and attributes for TMS - 2 hr 30 mins, rafi meeting - 1hr, Relationship mapping - 30 mins | others(lunch & tea break)-1.30hour
Ragu | Entity data model | Full UI design completed |  | discussion with team -30min,intergation of head ,co ordinator , trainer , trainee UI-100mins, meeting rafi 60 mins , creating reviewer work flow design and editing the course list - 60mis, reviewing the full uI work flow -120min. | lunch and break 1.30hrs
Sruthi | Class model with operations | Relationship mapping |  | Team meeting - 30 mins, Refining Entities and attributes for TMS - 2 hr 30 mins, rafi meeting - 1hr, MOM - 30 mins , Relationship mapping - 30 mins | Break - 1:30 mins
Sobhana | Entity Data model and its Relationship | Entity datamodel for all users |  | Team discussion- 30 mins, Meeting with rafi - 1hr, MOM - 30 mins ,Entities and attributes for TMS - 2 hr 30 mins, Relationship mapping - 30 mins | Lunch -45mins,Break-20 min
Arul | Behaviours of entity and view models | Data entry in TMS - 30 mins, TMS relation ship mapping - 30 mins, rafi meeting - 1hr, MOM - 30 mins | Exploration | Team meeting - 30 mins, client meeting - 1hr, Refining Entities and attributes for TMS - 2 hr 30 mins,MOM - 30 mins , Relationship mapping - 30 mins | lunch and others 130mins

## 13-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Trainer (ui) | Correcting work flow of trainee and reviewing the co-ordinator. |  | team discussion 30 mins,working on ui(trainee)-1 hr and 30 mins ,meeting with rafi 30 mins,working refining data model -1 hr,working on ui reviewing and consistent check(over all)-2:30hrs ,Total-5hrs and 30 mins | break 1 hr
Gokul | TMS Physical Data Model,TMS calss diagram with operations | team meeting - 30 mins,TMS data model refining - 2 hr 30 mins, Data entry in TMS - 30 mins, TMS relation ship mapping - 30 mins, rafi meeting - 1hr |  | 4hrs 30 mins | Lunch & break - 1hr 30 mins,teaching others - 1hr
Gokulraj | Date model, relationships and behaviour | TMS Full UI Design Flow |  | Team Disscussion 30 mins about Design Integration and Data Model, Integration on Training Head, Co-ordinator, Trainer, Trainee design flow 100 mins, Meeting with client (Rafi) - 60mins, Creating Reviewer Flow and Making Changes in Course Flow 60mins, Finalize the TMS Design Flow 120mins | Lunch and Tea break-90min
Iswarya |  | Review the Entire UI and relationship of datamodel |  | Team meeting - 30 mins, Relationship for Datamodel -30 mis, Understanding the 2 different datamodel-1 hr ,Team discussion for Datamodel relationship-2hr, Review the entire UI -2hr | Lunch and tea break -1.30 mins
Kavin | UI for Trainer in TMS | UI design work flowfor Training Co-ordinator and Trainer |  | Team meeting - 1.30hr, rafi meeting - 30mins,Entity data model relationship and UI design Trainee -2hrs | others(lunch & tea break)-90min
Kirubaharan | Behaviours of entity and view models | Data models entities and attributes |  | Discussion with team - 20 mins, meeting with 60 mins , Prepared MOM | Session with Anitha - 1 hour, prepared for presentation - 2 hours,Others- 1 hour 30 mins
Prathima | Entity data model operation for TMS | Entity datamodel ,artributes for TMS |  | Team meeting - 1.30hr, rafi meeting - 30mins,Entity data model relationship ,attributes,operation-2hrs | others(lunch & tea break)-1.30hour
Ragu | Entity data model | Full UI design completed |  | discussion with team -30min,intergation of head ,co ordinator , trainer , trainee UI-100mins, meeting rafi 60 mins , creating reviewer work flow design and editing the course list - 60mis, reviewing the full uI work flow -120min. | lunch and break 1.30hrs
Sruthi |  | Review the Entire UI |  | Team meeting - 30 mins, Understanding the datamodel-1 hr ,Team discussion for Datamodel relationship-2hr, Review the entire UI -2hr | Break - 1:30 mins
Sobhana | Entity Data model and its Relationship | Entity datamodel for all users |  | Team discussion- 30 mins, Meeting with rafi - 1hr, MOM - 30 mins ,Entities and attributes for TMS - 2 hr 30 mins, Relationship mapping - 30 mins | Lunch -45mins,Break-20 min
Arul | view model for a page | TMS physical model |  | Team discussion- 30 mins, Meeting with rafi - 1hr, MOM - 30 mins , Relationship mapping - 30 mins | lunch and others 130mins

## 15-4-22
#NAME? | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | HLD | UI(Trainer),Overall(consistent check),reviewing data model. |  | Team meet -20 mins,working on ui(over all)-3hrs,reviewing data model and convey the corrections-30mins,reviewing trainer(constraints,assumption,acceptance criteria)-30mins, | break -1:30 hrs
Gokul | angular cli exploration | TMS Physical Data Model,TMS calss diagram with operations |  | TMS Physical Data Model - 1 hr, TMS class diagram - 1 hr, TMS class diagram with operations - 1hr | angular cli cmd - 1hr 30 mins,lunch and break- 1hr
Gokulraj | Date model, relationships and behaviour | checking overall UI flow and checking flow , acceptance criteria, assumption, constraints |  | team meet 20mins, checking and editing overall UI -3hrs, checking flow , acceptance criteria, assumption, constraints (training head)- 30mis | Lunch and Tea break-90min
Iswarya |  | Refining the Trainer and Head Acceptance Criteria,constrain,assumption |  | Team meet in online-20 mins, Review the physical datamodel and class diagram-1hr, trainer and head Acceptance criteria,constrain and assumption-2hrs, review the trainig coordinator Acceptance criteria-20 mins | Session with Anitha-1 hr, worked with assignments given by anitha, Break - 1:30 hrs
Kavin | HLD | UI(Trainer),Overall(consistent check) in UI prototype |  | Meeting with Rafi-60 minutes,Worked on Trainer, and Trainee naming conversion and consistency-2 hours ,Discussion with team - 30mins | others(lunch & tea break)-100 min
Kirubaharan |  | Refined acceptance criteria for trainee flow |  | Team meet - 20 mins , Reviewed acceptance criteria for trainee - 2 hours , TMS physical data model - 1 hour | Lunch - 1 hour
Prathima |  | Acceptance criteria ,assumption,dependencies ,user stories for training co ordinator |  | Team meeting - 30mins, Refining user stories,acceptance creteria ,dependencies,assumption for training co ordinator-2.30hrs
Ragu | Entity data model | checking overall UI flow and checking flow , acceptance criteria, assumption, constraints |  | team meet 20mins, checking and editing overall UI -3hrs, checking flow , acceptance criteria, assumption, constraints (training head)- 30mis | lunch -1hr
Sruthi |  | Refining the Trainer and Head Acceptance Criteria,constrain |  | Team meet in online-20 mins, Review the physical datamodel and class diagram-1hr, trainer and head Acceptance criteria,constrain and assumption-2hrs, review the trainig coordinator Acceptance criteria-20 mins
Sobhana | Entity Data model and its Relationship | Entity datamodel for all users |  | Team discussion- 30 mins, Meeting with rafi - 1hr, MOM - 30 mins ,Entities and attributes for TMS - 2 hr 30 mins, Relationship mapping - 30 mins | Lunch -45mins,Break-20 min
Arul | View model for a page | Physical Data model and acceptance criteria and assumption and constrains for trainee |  | Team meet - 20 mins , Reviewed acceptance criteria for trainee - 2 hours , TMS physical data model - 1 hour | lunch and others 130mins

## 18-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | HLD | Entity Framework(self exploration) |  | meeting with team-30 mins(HLD) | Preparing for review(webapi)-3 hrs,self exploration-2 hrs.total-5 hrs
Gokul | HLD | Explored Angular components, data binding, passing data from parent to child, from child to parent, life cycles of angular components etc. |  | Team discussion 30mins | angular 5hrs, typescript 30mins, lunch and break 1hr 30mins
Gokulraj | Date model, relationships and behaviour | checking overall UI flow and checking flow , acceptance criteria, assumption, constraints |  | team meet 20mins, checking and editing overall UI -3hrs, checking flow , acceptance criteria, assumption, constraints (training head)- 30mis | Lunch and Tea break-90min
Iswarya | HLD for TMS | Self Exploration |  | 30 mins : Team discussion | 1hr : WebAPI basic 2hrs : Angular 1hr : implemented the learned concept
Kavin | HLD | UI(Trainer),Overall(consistent check) in UI prototype |  | Meeting with Rafi-60 minutes,Worked on Trainer, and Trainee naming conversion and consistency-2 hours ,Discussion with team - 30mins | others(lunch & tea break)-100 min
Kirubaharan | HLD for TMS | Explored on Angular 1 hour30 mins , Web API basics 1 hour 30 mins |  | Team meeting - 30 mins | Others ( Lunch and Tea break)-1 hour 30 mins
Prathima | HLD for TMS | Self Exploration |  | 30 mins : Team discussion | exploration on entity framework, and web API-2.30hrs
Ragu | Entity data model | checking overall UI flow and checking flow , acceptance criteria, assumption, constraints |  | team meet 20mins, checking and editing overall UI -3hrs, checking flow , acceptance criteria, assumption, constraints (training head)- 30mis | lunch -1hr
Sruthi | HLD for TMS | Self Exploration |  | Team discussion about Hld - 30 mins | basic concepts on angular and web api- 3 hrs, lunch break - 1 hr
Sobhana | HLD for TMS | Entity datamodel for all users |  | Team discussion- 30 mins, Meeting with rafi - 1hr, MOM - 30 mins ,Entities and attributes for TMS - 2 hr 30 mins, Relationship mapping - 30 mins | Lunch -45mins,Break-20 min
Arul | HLD for TMS | Exploration on Angular, Entity Framework |  | Team meeting - 30 mins | lunch and others 130mins

## 19-04-22
Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | HLD | Entity Framework(self exploration) |  | meeting with team-30 mins(HLD) | Preparing for review(webapi)-3 hrs,self exploration-2 hrs.total-5 hrs
Gokul | angular exploration | system architecture |  | Team discussion 30mins, system architecture - 1 hr, reviewed data dictonary - 30mins,helped in view model - 30 mins, | angular 4hrs, lunch and break 1hr 30mins
Gokulraj | Date model, relationships and behaviour | checking overall UI flow and checking flow , acceptance criteria, assumption, constraints |  | team meet 20mins, checking and editing overall UI -3hrs, checking flow , acceptance criteria, assumption, constraints (training head)- 30mis | Lunch and Tea break-90min
Iswarya | HLD for TMS | View Model for TMS. Non-functional Requirements in HLD |  | 30mins : Team discussion, 1hr : View model,1hr : non-functional Requirements, | 3hr : Exploring Angular 1hr: Exploring Typescript
Kavin | HLD | UI(Trainer),Overall(consistent check) in UI prototype |  | Meeting with Rafi-60 minutes,Worked on Trainer, and Trainee naming conversion and consistency-2 hours ,Discussion with team - 30mins | others(lunch & tea break)-100 min
Kirubaharan | angular exploration | Flow chart for Trainee flow |  | Team meeting - 30 mins, Angular 2 hours, Re explored the concepts of SQL,C#, | Others ( Lunch and Tea break)-1 hour 30 mins
Prathima | HLD for TMS | Self Exploration |  | 30 mins : Team discussion | exploration on entity framework, and web API-2.30hrs
Ragu | Entity data model | checking overall UI flow and checking flow , acceptance criteria, assumption, constraints |  | team meet 20mins, checking and editing overall UI -3hrs, checking flow , acceptance criteria, assumption, constraints (training head)- 30mis | lunch -1hr
Sruthi | HLD for TMS | View Model for TMS. Design Principles and introduction in HLD |  | Team discussion - 30 mins,View model - 1hr | Explored on angular - 2hrs,typescript - 1 hr
Sobhana | HLD for TMS | Entity datamodel for all users |  | Team discussion- 30 mins, Meeting with rafi - 1hr, MOM - 30 mins ,Entities and attributes for TMS - 2 hr 30 mins, Relationship mapping - 30 mins | Lunch -45mins,Break-20 min
Arul | HLD for TMS | Exploration on Angular, Entity Framework |  | Team meeting - 30 mins | lunch and others 130mins