## 5-4-22
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Sharing the points on Individual User Story,Refining the Workflow | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Gokul | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Gokulraj | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Iswarya | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Kavin | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Kirubaharan | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Prathima | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Ragu | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30
Sruthi | Requirements refining ,prototype disscussion,Rafi Session-Abstract Pattern | User Stories, User WorkFlow | Mentor,Delivery Head | 5:30 | 2:30
Sobhana | Requirements refining ,prototype disscussion | User Stories, User Flow | Mentor,Delivery Head | 5:30 | 2:30

## 6-4-22
Resource Name | Action Point / Impediments | Status | Comments
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Discussion About User Stories And User Flow.Session With Rafi.Started Designing UI,Discussion About Estimation | Prototype,Constraints,Assumption | Acceptance criteria | 6:30 | 1:00
Gokul | trainee flow mockups, prototypes | landing page, dashboard page, courses page,attendance page, feedback page |  | rafi meeting - 1hr, team meeting - 2hr, UI templates - 2hr, total time - 5hr | figma - 1hr 30 mins, lunch & tea break - 1 hr 15 mins, total time - 2 hr15 mins
Gokulraj | Working on Constraints, Assumptions. | Discuss with Rafi about Userstory, Correction in Userstory, Discussion about Prototype, Working on Acceptance Cretiria. |  | Rafi Meeting - 1hour, Userstory - 15min, Team Disscussion - 2 hours, Prototype - 2.5 hours, Acceptance Criteria - 30min. Toatal 6.15 Hours | Figma tutorial - 30min
Iswarya | Acceptance criteria | Discussion with rafi about user story and user flow,Team discussion about prototype,UI designing. |  | 5:30 | 2:30
Kavin | Working on UI designing ,Acceptance criteria | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story |  | rafi meeting - 1hr, team meeting - 2hr, UI templates,acceptance certeria - 2.5hr, total time - 5.30hr | 2:30
Kirubaharan | Working on Acceptance criteria,constraints and Assumption | Meeting with client about user story and userflow,Team discussion about prototype | Acceptance criteria | 5:30 | 2:30
Prathima | Working on UI designing ,Acceptance criteria | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story,user flow |  | rafi meeting - 1hr, team meeting - 2hr, UI templates,acceptance certeria - 2.5hr, total time - 5.30hr | 2:30
Ragu | working on constraints, assumptions. | Discuss with Rafi about user story, correction in user story, discussion about prototype, working on acceptance cretiria. |  | Rafi Meeting - 1hour, Userstory - 15min, Team Disscussion - 2 hours, Prototype - 2.5 hours, Acceptance Criteria - 30min. Toatal 6.15 Hours | Figma tutorial - 30min
Sruthi | Acceptance criteria | Discussion with rafi about user story and user flow,Team discussion about prototype,UI designing. |  | 5:30 | 2:30
Sobhana | Working on UI designing ,Acceptance criteria,constraints | Meeting with Rafi about user story and userflow,Team discussion about prototype,refining the user story,user flow |  | rafi meeting - 1hr, team meeting - 2hr, UI templates - 2hr,constraints and acceptance criteria-30 min, total time - 5.30hr | 2:30
Arul | Understanding existing work done by team members

## 7-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Landing page(Trainer) | Trainer Pages( My course , Topics,Assignments,Feedback) |  | Assumption and Constraints -50mis,Meeting With rafi-45 mins,Team Discussion-50 mins,Creating UI Templates -2:15 hrs ,Total Time-4:40hrs | Session With Rafi(Builder Pattern)-30mins,Softskill Session-45 mins,others 20mins,Abstract Design Pattern-40mins ,Non Project-2:15 hrs
Gokul | prototype for trainee | Trainee requirements refining ,designed 8 pages for trainee, |  | Meeting With rafi - 45 mins,Team Discussion - 50 mins,created trainee pages - 3:00 hrs ,Total Time - 4:45 | abstratct pattern - 45 mins, lunch - 45 mins, break - 30 mins, total time -2 hrs
Gokulraj |  | Training Head - Acceptance Cretiria, Constraints, Assumptions. | Previous UI design has been discarded | Meeting with Client Rafi(About UI design)-45min, Team Discussin about UI design-60min, Making changes in Training Haed Acceptance Cretiria, Constraints, Assumptions-90min,Discussion with Teammate about Acceptance Cretiria, Constraints, Assumptions and UI design(Training Head)-60min. | Abstract Pattern Session-40min, others(lunch & tea break)-90min
Iswarya |  | UI designing on trainer - landing page,feedback page | Previous UI design has been discarded | Worked on acceptance criteria and UI design - 1:30 mins,Prototype disscussion with rafi - 45 mins,team discussion about modification on prototype - 50 mins, Trainer Landpage,feedback page-1 hr | Abstract Pattern-40 mins,Softskill Session-45 mins,
Kavin | UI design (dashboard )for training co ordinator | UI design for training Co-Ordinator | Previous UI design has been refined | Meeting with rafi (reviewed UI design )-1hr Discussion with team about UI design-1hr UI design for training Co-Ordinator-2hrs Discussion with Prathima for UI design for training Co Ordinator-1hr | Abstract Pattern Session-40min lunch,break-1.30hr
Kirubaharan |  | Assumption, Acceptance Criteria and constraints for Trainee stories | Prototype design | Discussion with team members about UI prototype - 40 mins, Worked on Acceptance criteria ,assumption and constraints for Trainee - 2 hours,Meeting with Rafi - 1 hour, | Design pattern session - 40 mins ,softskill session- 50 mins,Others - 1 hour 20 mins
Prathima | UI design (dashboard )for training co ordinator | Meeting with rafi (reviewed UI design ),acceptance criteria,containts,assumption for training co ordinator |  | Meeting with rafi (reviewed UI design )-1hr Discussion with team about UI design-1hr Completed acceptance criteria,assumption,Contraints for training co-ordination user stories.-2hrs Discussion with Kavin for UI design for training Co Ordinator-1hr | Abstract Pattern Session-40min lunch,break-1.30hr
Ragu | Landing page(Co ordinator) | Training head - UI designing ( Login page,dashboard,register page, View status page, Filter page) | Previous UI design has been discarded | Meeting with Rafi( about UI designing)- 45min, team discussion about UI designing -1hr, completed UI design for training head(Login page,dashboard,register page, View status page, Filter page)-3hrs discussion with teamate about acceptance criteria and constraints fro training head - 1hr. | Abstract pattern session - 40min lunch and break 1.30hrs
Sruthi |  | Trainer - constraints, acceptance criteria, assumptions | Previous trainer UI design has been discarded | Worked on acceptance criteria and UI design - 1:30 mins,Prototype disscussion with rafi - 45 mins,team discussion about modification on prototype - 50 mins, Trainer - constraints, acceptance criteria, assumptions - 1 hr | Session with Rafi about abstract pattern - 40 mins
Sobhana | UI design (dashboard )for training co ordinator | Meeting with rafi (reviewed UI design ),acceptance criteria,containts,assumption for training co ordinator,Refining UI for co-ordinator | Previous UI design has been discarded | Meeting with client-1hr Discussion with team about UI design-1hr acceptance criteria,assumption,Contraints for training co-ordinater for user stories.-1.30hrs UI design for training Co Ordinator-1.30hr | abstract pattern - 45 mins, lunch - 45 mins, break - 20 mins
Arul | Refining trainee user stories | Assumption, Acceptance Criteria and constraints for Trainee stories | Prototype design | Meeting with client - 45mins,I've discussed about UI protyping with team members - 45mins, Done acceptance criteria for Trainee user stories - 120 mins | Softskill Session-45 mins, Design pattern session ,others 90mins

## 8-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Trainer | Co-Ordinator(Schedule Review,attendance,Course flow),Trainee(Feedback,Assignment,Mom) |  | Workflow Integration-1 hr,Reviewing-1 hr,Meeting With Rafi-1:40 hrs,Worked On Ui For Co-ordinator-2 hrs,ui Trainer-1 hr,Total Time-6:40 hrs | Break-1 hr
Gokul | ABSENT | ABSENT |  | ABSENT | ABSENT
Gokulraj | Designing prototype | Entities and Data Model Rough |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design and Entity - 120mins, Correction in Design - 60mins | Builder Pattern Session-60min, Photo Shoot at BasketBall court - 60 mins, others(lunch & tea break)-90min
Iswarya |  | Trainer course,topic,assignment,list of trinee and their detail page UI Design |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design and Entity - 120mins, Correction in Design - 60mins
Kavin | UI design for training co ordinator and Training head refining | Training head login,register,Dashboard and List of department |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design-120 min, Training head Design - 60mins and Prepare for presentation in Adaptor pattern-60 mina | Pattern Session-60min, Photo Shoot at Volleyball court - 60 mins, others(lunch & tea break)-1.15hour
Kirubaharan |  | Trainee acceptance criteria, Constraints and assumption |  | Meeting with Rafi -50 mins,Corrections in Design - 60 mins,Team discussion about entity and design -180 mins | Builder pattern session-60 mins,Friday activities-60 mins, Others - 90 mins
Prathima | UI design (dashboard )for training co ordinator,entity framework and requirements | UI for trainee |  | Meeting with Rafi -1hr(reviewed UI Design)Corrections in Design - 1hr,Team discussion about entity and design -2hrs | Builder Design Pattern and prototype Session-1hr, Photo Shoot at basketball court - 1hr, others(lunch & tea break)-1.30hr
Ragu | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sruthi |  | ABSENT | ABSENT | ABSENT | ABSENT
Sobhana | UI design (dashboard )for training co- ordinator | UI for training coordinator | Previous UI design has been discarded | Meeting with Rafi -1hr,Corrections in Design - 1hr,Team discussion about entity and design -3hrs | Builder Design Pattern and prototype Session-1hr, Photo Shoot at basketball court - 1hr, others(lunch & tea break)-1.30hr ,review-45min
Arul | Designing prototype | Entities and Data model | Exploration | Meeting with client - 45mins,I've discussed about User flow team members - 120mins, Done entity model rough - 60 mins | Softskill -45 mins, Design pattern session ,others 90mins

## 9-4-22
- | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Entity ,Attributes | Training Co-ordinator(Review,Assignment),Consistent check in Training Co-ordinator |  | Team discussion - UI Integration -45 mins, Refining Flow Correction 2 hrs,Consistent Check-2hrs,ui design(Co-ordinator,Trainee) 2 hrs,Meeting With Rafi-1:45 hrs.Total 8:45 hrs | Break-1:00 hr
Gokul | ABSENT | ABSENT |  | ABSENT
Gokulraj | Training head and training co-ordinator refining | Training Head UI page |  | Team meeting -60mins ,Correction in UI design-2hrs, entity frame work and datamodel -90 min ,Meeting with Rafi -1.45hours(reviewed UI Design) | others(lunch & tea break)-90min
Iswarya | Data Model | Trainer course,topic,assignment,list of trinee and their detail page UI Design |  | Training co-ordinator UI Discussion-1.30 hrs and design-3hrs,Meeting with Rafi -1.30 hrs. Sunday Trainer UI correction and Design-3hrs
Kavin | UI design for training co ordinator (Assign course,review ,and attendance) | Ui design Training Co-ordinator Dashboard and create course ,assign courseand prepare for presentation in design pattern |  | Prepare for presentation in design pattern -90 min ,Meeting with client (Rafi) - 1.45hours,Team meeting -60mins | Others(lunch & tea break)-1.30hour
Kirubaharan |  | Consistency checking in Trainee, Entity modeling |  | Team discussion about UI integration - 45 mins , Entity modelling - 1 hour,consistency checking - 2 hours,review with Rafi - 100 mins | Lunch and other breaks - 1 hour 30 mins
Prathima | Entity ,Attributes | UI design for training co ordintor(schedule review),dashboard for training co-cordinator,trainee,trainer,training head, Entity framework and data model |  | Team meeting -60mins ,Correction in UI design-2hrs, entity frame work and datamodel -90 min ,Meeting with Rafi -1.45hours(reviewed UI Design) | others(lunch & tea break)-1.30hr
Ragu | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sruthi | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sobhana | UI design (dashboard )for training co- ordinator | UI for trainee and trainer |  | Group discussion about UI integration - 45 mins , Entity modelling - 1 hour,Consistency checking - 2 hours,Meeting with rafi - 1.45 mins | Lunch : 1hour, Break:20 mins
Arul |  | Entities and Data model |  | Group discussion about UI integration - 45 mins , Entity modelling - 1 hour,Consistency checking - 2 hours,Session with Rafi - 100 mins | Break-2:00 hr

## 11-4-22
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Asuvath | Trainer UI | Co-Ordinator(Schedule Review,attendance,Course flow),Trainee(Feedback,Assignment,Mom) |  | Workflow Integration-1 hr,Reviewing-1 hr,Meeting With Rafi-1:40 hrs,Worked On Ui For Co-ordinator-2 hrs,ui Trainer-1 hr,Total Time-6:40 hrs | Break-1 hr
Gokul | Entity relationships, Entity attributes | Completed Changes in Trainee Design, Completed changes in Trainer Design, Worked on Data Models in TMS |  | Changes in Trainee Design - 2hr,Meeting With Rafi - 1hr 30 mins, Data Models - 1hr 30 mins total hrs- 5hrs | Lunch and break 1hr 15 mins, self exploration - entity frame work - 1hr total hrs - 2 hrs 15 mins
Gokulraj | Designing prototype | Entities and Data Model Rough |  | Meeting with client (Rafi) - 50mins, Team Discussion about Design and Entity - 120mins, Correction in Design - 60mins | Builder Pattern Session-60min, Photo Shoot at BasketBall court - 60 mins, others(lunch & tea break)-90min
Iswarya | Data model Relationship | Entities and Data Model Rough |  | Team discussion-15 mins,working with Data model-2hrs, Meeting with client (Rafi) - 1.30 hrs | Preparing for review-2.30hrs, Attending Review-50 mins
Kavin | UI design for training co ordinator and Trainee consistency and naming conversion | Training head login,register,Dashboard and List of department |  | Meeting with Rafi-100 minutes,Worked on Training Head naming conversion and consistency-2 hours ,Discussion with team - 20 mins | others(lunch & tea break)-1.30hour
Kirubaharan | Designing Entity data model for Trainee | Reviewed acceptance criteria for Trainee ,Trainer,training coordinator,Training head, Updated MOM |  | Discussion with team - 20 mins, Worked on entity data model for trainee and collaborated with others-120 mins,meeting with Rafi- 100 mins | Prepared for code review - 1 hour , others - 90 mins
Prathima |  | UI for trainee |  | Meeting with Rafi -1hr(reviewed UI Design)Corrections in Design - 1hr,Team discussion about entity and design -2hrs | Builder Design Pattern and prototype Session-1hr, Photo Shoot at basketball court - 1hr, others(lunch & tea break)-1.30hr
Ragu | ABSENT | ABSENT | ABSENT | ABSENT | ABSENT
Sruthi | Data model Relationship | Entities and attributes for all users |  | Team discussion-15 mins,working with Data model-2hrs, Meeting with client (Rafi) - 1.30 hrs,Prepared data model for all users - 3 hrs | Break - 1 hr
Sobhana | UI design (dashboard )for training co- ordinator | UI for training coordinator | Previous UI design has been discarded | Meeting with Rafi -1hr,Corrections in Design - 1hr,Team discussion about entity and design -3hrs | Builder Design Pattern and prototype Session-1hr, Photo Shoot at basketball court - 1hr, others(lunch & tea break)-1.30hr ,review-45min
Arul | Designing Entity data model for Trainee | Reviewed acceptance criteria for Trainee, Trainer, Training co ordinator, Trainnig Head. | Exploration | Meeting with client - 90 mins, I've decided to work on entity data model for trainee and Integrated others- 120mins, Done entity model rough - 60 mins | lunch and others 130mins