## Actual Plan
WEEK 0 | 2022-03-21 | DAY 0 | INTRODUCTION AND ASSESSMENT | Completed
| 2022-03-22 | DAY 1 | REQUIREMENT PHASE | Completed
| 2022-03-23 | DAY 2 |  | Completed
| 2022-03-24 | DAY 3 | DESIGN PHASE | Completed
| 2022-03-25 | DAY 4 |  | Completed
WEEK 1 | 2022-03-28 | DAY 5 | DESIGN PHASE | Completed
| 2022-03-29 | DAY 6 |  | Completed
| 2022-03-30 | DAY 7 | CODING AND TESTING PHASE | Completed
| 2022-03-31 | DAY 8 |  | Completed
| 2022-04-01 | DAY 9 | PROJECT MANAGEMENT | Completed
| 2022-04-02 | DAY 10 | PROJECT KICKOFF | Completed
WEEK 2 | 2022-04-04 | DAY 11 | SPRINT 0 - Requirements Phase | Completed
| 2022-04-05 | DAY 12 |  | Completed
| 2022-04-06 | DAY 13 |  | Completed
| 2022-04-07 | DAY 14 |  | Completed
| 2022-04-08 | DAY 15 |  | Completed
| 2022-04-09 | DAY 16 | SPRINT 1 - Design Phase | Completed
WEEK 3 | 2022-04-11 | DAY 17 | SPRINT 1 - Design Phase | Completed
| 2022-04-12 | DAY 18 |  | Completed
| 2022-04-13 | DAY 19 |  | Completed
WEEK 4 | 2022-04-20 | DAY 20 | SPRINT 1 - Design Phase | Completed
| 2022-04-21 | DAY 21 |  | Completed
| 2022-04-22 | DAY 22 | SPRINT 2 - Coding Phase | Completed
| 2022-04-23 | DAY 23 |  | Completed
WEEK 5 | 2022-04-25 | DAY 24 | SPRINT 2 - Coding Phase | Completed
| 2022-04-26 | DAY 25 |  | Completed
| 2022-04-27 | DAY 26
| 2022-04-28 | DAY 27 | SPRINT 3 - Coding Phase
| 2022-04-29 | DAY 28
| 2022-04-30 | DAY 29
WEEK 6 | 2022-05-05 | DAY 30 | SPRINT 3 - Coding Phase
| 2022-05-06 | DAY 31
| 2022-05-07 | DAY 32 | SPRINT 4 - Testing Phase
WEEK 7 | 2022-05-09 | DAY 33 | SPRINT 4 - Testing Phase
| 2022-05-10 | DAY 34
| 2022-05-11 | DAY 35
| 2022-05-12 | DAY 36
| 2022-05-13 | DAY 37 | SPRINT 5 - Finalizing Phase
| 2022-05-14 | DAY 38
WEEK 8 | 2022-05-16 | DAY 39 | SPRINT 5 - Finalizing Phase
| 2022-05-17 | DAY 40
| 2022-05-18 | DAY 41
| 2022-05-19 | DAY 42 | PROJECT REVIEW
| 2022-05-20 | DAY 43
| 2022-05-21 | DAY 44

## Revised Plan
Day | Date | Phase | Work
Monday | 2022-05-09 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Tuesday | 2022-05-10 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Wednesday | 2022-05-11 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Thursday | 2022-05-12 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Friday | 2022-05-13 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Saturday | 2022-05-14 | Coding Phase | Web API + Angular Component Creation Completion | Yes
Week 20 | 2022-05-14 | Status | Send the status as per the given table
Sunday | 2022-05-15 | LEAVE
Monday | 2022-05-16 | Coding Phase | Angular and Web API Integration | Yes
Tuesday | 2022-05-17 | Coding Phase | Angular and Web API Integration | Yes
Wednesday | 2022-05-18 | Coding Phase | Angular and Web API Integration | Yes
Thursday | 2022-05-19 | Coding Phase | Angular and Web API Integration | Yes
Friday | 2022-05-20 | Coding Phase | Angular and Web API Integration | Yes
Saturday | 2022-05-21 | Coding Phase | Angular and Web API Integration | Yes
Saturday | 2022-05-21 | Coding Phase | Angular and Web API Integration | Yes
Week 21 | 2022-05-22 | Status | Send the status as per the given table
Monday | 2022-05-23 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Tuesday | 2022-05-24 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Wednesday | 2022-05-25 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Thursday | 2022-05-26 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Friday | 2022-05-27 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Saturday | 2022-05-28 | Coding Phase | Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | No
Week 22 | 2022-05-28 | Status | Send the status as per the given table
Sunday | 2022-05-29 | LEAVE
Monday | 2022-05-30 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing | yes(SonarQube) | No( Liniting and Coverage for angular ,Load testing,security testing)
Tuesday | 2022-05-31 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing | yes(SonarQube) | No( Liniting and Coverage for angular ,Load testing,security testing)
Wednesday | 2022-06-01 | Coding Phase | Refactoring - Static Analysis of C# (SonarQube) and Liniting and Coverage for Angular + Load Testing with Jmeter + Security Testing | yes(SonarQube) | No( Liniting and Coverage for angular ,Load testing,security testing)
Thursday | 2022-06-02 | Coding Phase | Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) | No
Friday | 2022-06-03 | Coding Phase | Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) | No
Saturday | 2022-06-04 | Coding Phase | Usability Testing - Lighthouse, https://validator.w3.org/ + Deploying into AWS portal and Setting Pipelines (Build and Deploy 2 Stages) | No
Week 23 | 2022-06-04 | Status | Send the status as per the given table
Sunday | 2022-06-05 | LEAVE
Monday | 2022-06-06 | Testing Phase | Test Scenarios and Test Case Preparation | No
Tuesday | 2022-06-07 | Testing Phase | Test Scenarios and Test Case Preparation | No
Wednesday | 2022-06-08 | Testing Phase | Test Scenarios and Test Case Preparation | No
Thursday | 2022-06-09 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Friday | 2022-06-10 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Saturday | 2022-06-11 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Week 24 | 2022-06-11 | Status | Send the status as per the given table
Sunday | 2022-06-12 | LEAVE |  | No
Monday | 2022-06-13 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Tuesday | 2022-06-14 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Wednesday | 2022-06-15 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Thursday | 2022-06-16 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Friday | 2022-06-17 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Saturday | 2022-06-18 | Testing Phase | Application Testing and Defects Tracking and Fixing | No
Week 25 | 2022-06-18 | Status | Send the status as per the given table
Sunday | 2022-06-19 | LEAVE
Monday | 2022-06-20 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Tuesday | 2022-06-21 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Wednesday | 2022-06-22 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Thursday | 2022-06-23 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Friday | 2022-06-24 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Saturday | 2022-06-25 | Finalization Phase | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | No
Week 26 | 2022-06-25 | Status | Send the status as per the given table
Sunday | 2022-06-26 | LEAVE
Monday | 2022-06-27 | Review | Reviewing the Application of all above mentioned activities | No
Tuesday | 2022-06-28 | Review | Reviewing the Application of all above mentioned activities | No
Wednesday | 2022-06-29 | Review | Reviewing the Application of all above mentioned activities | No
Thursday | 2022-06-30 | Review | Reviewing the Application of all above mentioned activities | No
Friday | 2022-07-01 | Review | Reviewing the Application of all above mentioned activities | No
Saturday | 2022-07-02 | LEAVE
Sunday | 2022-07-03 | LEAVE
Monday | 2022-07-04 | Demo | Demostration to Training and Delivery Team
Tuesday | 2022-07-05 | Demo | Demostration to Training and Delivery Team | No
Wednesday | 2022-07-06 | Demo | Demostration to Training and Delivery Team | No
Thursday | 2022-07-07 | Summary | Refershing all the topics and Feedbacks | No
Friday | 2022-07-08 | Summary | Refershing all the topics and Feedbacks | No
Saturday | 2022-07-09 | LEAVE |  | No
Sunday | 2022-07-10 | LEAVE

## References
.NET Test Explorer | https://codemag.com/Article/2009101/Interactive-Unit-Testing-with-.NET-Core-and-VS-Code?msclkid=39ec497bd10a11ec9fc571f847c244bb
https://levelup.gitconnected.com/unit-testing-best-practices-in-net-c-3117ea4010b9?sk=5b4cdac557b3e56d97365669a12aa198
Angular - Testing | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_test.htm
Linting | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_lint.htm
Doumentation | https://www.tutorialspoint.com/angular_cli/angular_cli_ng_doc.htm
Pipelines | https://docs.aws.amazon.com/codepipeline/latest/userguide/tutorials-four-stage-pipeline.html#tutorials-four-stage-pipeline-add-stage
Security Testing | Automated Security Testing Using OWASP ZAP with Examples! (swtestacademy.com)
Performance Testing | https://www.simplilearn.com/tutorials/jmeter-tutorial/jmeter-api-testing
https://www.youtube.com/watch?v=HiRZq9_xDjg
Code Analysis | https://www.c-sharpcorner.com/article/step-by-step-sonarqube-setup-and-run-sonarqube-scanner/

## Status Template - WEEK <No>
Work Items | Completed | In Progress | Yet to start
Low Level Design | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Web API Implementation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Angular Component Creation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Web API and Angular Integration | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Refactoring and Deployment | * Source Code Repo | * Source Code Repo | * Source Code Repo
Test Scenarios and Test Case Preparation | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Application Testing and Defects Tracking and Fixing | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features
Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | * Features * Features * Features | * Features * Features * Features | * Features * Features * Features

## Test Plan Template
<Project Name>Test Plan - <Cycle Number>
Scope of Test |  | Features Included | < Identify all software features and combinations of software features that will be tested.>
|  | Features Excluded | <Identify all features and significant combinations of features which will not be tested and the reasons.>
Test Deliverables |  |  | Identify the deliverable documents. You can list the following documents: - Test Plan - Test Cases - Test Incident Reports - Test Summary Reports>
Test Dependencies |  |  | <Identify significant constraints on testing, such as test-item availability, testing-resource availability, and deadlines.>
Test Environment |  | Hardware Environment | <Include the minimum hardware requirements that will be used to test the Application.>
Software Environment
Network and Communication
Test Items
S.No | Test Item |  | Source | [6 empty] | Version
Test Schedule
No. | Build | Features |  | Start Date | End Date | Actual Start Date | Actual End Date | Est Effort (in Hrs) | Actual Effort (in Hrs) | Completion % | Status
1
2
3
4
[5 empty] | Total |  | Total | 0 | 0 | #DIV/0!
Resources - Roles and Responsibilities
No. | Resource Name | Roles |  | Responsibilities
1
2
3
Depedencies
No. | Category | Description
1 | Software
2 | Resource
3 | Hardware
Assumptions
No. | Description
1
2
3

## Test Scenario Template
<Project Name><Smoke/Functional/Integration/ System/UAT> Test Scenarios
Type of Testing: Smoke/Functional/Integration/NFR/System Testing/UAT
Reference Documents :
Assumptions /Constraints :
Date : 08/07/2022
Scenario ID | Requirement ID | Module/Feature | Scenario Description
S-1 | 1 | HomePage | Homepage
S-2 |  | Login | Loginpage -> Enter credentials ->login
S-3 |  | To view Dashboard | Homepage ->dashboard
S-4 |  | To view Profile | Homepage ->My Profile
S-5 |  | To view Coordinator | Homepage ->Coordinator / Dashboard -> coordinator
S-6 |  | To add Coordinator | Homepage ->Coordinator -> AddUser / Dashboard -> coordinator ->AddUser
S-7 |  | To Edit Coordinator | Homepage ->Coordinator -> EditUser
S-8 |  | To disable Coordinator | Homepage ->Coordinator -> DisableUser
S-9 |  | To view Department | Homepage -> Departments/ Dashboard -> Department
S-10 |  | To view Trainer | Homepage -> Trainer/ Dashboard -> Trainer
S-11 |  | To view Trainee | Homepage -> Trainee/ Dashboard -> Trainee
S-12 |  | To view Reviewer | Homepage -> Reviewer/ Dashboard -> Reviewer
S-1 | 2 | HomePage | Homepage
S-2 |  | Login | Loginpage -> Enter credentials ->login
S-3 |  | To view Dashboard | Homepage -> Dashboard
S-4 |  | To view Profile | Homepage -> My profile
S-5 |  | To view Department | Homepage -> Departments/ Dashboard -> Department
S-6 |  | To add Department | Homepage -> Department -> Add / Dashboard ->Department ->Add
S-7 |  | To Edit Department | Homepage -> Department -> Edit / Dashboard ->Department ->Edit
S-8 |  | To disable Department | Homepage -> Department -> Disable / Dashboard ->Department->Disable
S-9 |  | To view Trainer | Homepage -> Trainer/ Dashboard -> Trainer
S-10 |  | To add Trainer | Homepage -> Trainer -> Add / Dashboard ->Trainer->Add
S-11 |  | To Edit Trainer | Homepage -> Trainer -> Edit / Dashboard ->Trainer ->Edit
S-12 |  | To disable Trainer | Homepage -> Trainer -> Disable / Dashboard ->Trainer->Disable
S-13 |  | To view Trainee | Homepage -> Trainee/ Dashboard -> Trainee
S-14 |  | To add Trainee | Homepage -> Trainee -> Add / Dashboard ->Trainee->Add
S-15 |  | To Edit Trainee | Homepage -> Trainee -> Edit / Dashboard ->Trainee ->Edit
S-16 |  | To disable Trainee | Homepage -> Trainee -> Disable / Dashboard ->Trainee->Disable
S-17 |  | To view Reviewer | Homepage -> Reviewer/ Dashboard -> Reviewer
S-18 |  | To add Reviewer | Homepage -> Reviewer -> Add / Dashboard ->Reviwer->Add
S-19 |  | To Edit Reviewer | Homepage -> Reviewer -> Edit / Dashboard ->Reviewer ->Edit
S-20 |  | To disable Reviewer | Homepage -> Reviewer -> Disable / Dashboard ->Reviewer->Disable
S-21 |  | To view Courses | Homepage -> Courses / Dashboard ->Courses
S-21 |  | To add Course | Homepage -> Course -> Add / Dashboard ->Course->Add
S-22 |  | To Edit Course | Homepage -> Course -> Edit / Dashboard ->Course ->Edit
S-23 |  | To disable Course | Homepage -> Course -> Disable / Dashboard ->Course->Disable
S-24 |  | To view Users in Coures | Homepage ->Course -> AddUsers
S-25 |  | To add User in Course | Homepage ->Course -> AddUsers -> Add
S-26 |  | To Remove User in course | Homepage ->Course -> AddUsers -> Remove
S-27 |  | To add Topic | Homepage -> Course ->Add Topic
S-28 |  | To Edit Topic | Homepage -> Course ->Edit Topic
S-29 |  | To disable Topic | Homepage -> Course ->Edit Topic
S-30 |  | To view Upcoming review | Homepage ->Upcoming review
S-31 |  | To add Reviewer | Homepage -> Upcoming review ->Add
S-32 |  | To View Completed review | Homepage -> Completed review
|  | To give Course feedback | Homepage->Courseview->give feedback
|  | To view trainee feedback | Homepage->Course->Trainee->Viewfeedback
S-1 | 3 | HomePage | Homepage
S-2 |  | Login | Loginpage -> Enter credentials ->login
S-3 |  | To view Dashboard | Homepage -> Dashboard
S-4 |  | To view Profile | Homepage -> My profile
S-5 |  | To view courses | Homepage -> My course
S-6 |  | To mark attendance | Homepage -> My course -> Topic -> Attendance
S-7 |  | To give assignment | Homepage -> Courses -> Topic -> AddAssignment
|  | To give Trainee feedback | Homepage->Trainee->TraineeList->Give Feedback
S-1 | 4 | HomePage | Homepage
S-2 |  | Login | Loginpage -> Enter credentials ->login
S-3 |  | To view Dashboard | Homepage -> Dashboard
S-4 |  | To view Profile | Homepage -> My profile
S-5 |  | To View Courses | Homepage -> My courses
S-6 |  | To view Topics | Homepage -> My courses -> Topic
S-7 |  | To mark attendance | Homepage -> My course -> Topic -> Attendance
S-8 |  | To submit assignment | Homepage -> Courses -> Topic -> Submit Assignment
S-9 |  | To view Upcoming review | Homepage -> Upcoming review
S-10 |  | To View Completed review | Homepage -> Completed review
S-11 |  | To Submit MOM | Homepage -> Completed review ->Submit MOM
S-12 |  | To View MOM | Homepage -> Completed review ->View MOM
S-1 | 5 | HomePage | Homepage
S-2 |  | Login | Loginpage -> Enter credentials ->login
S-3 |  | To view Dashboard | Homepage -> Dashboard
S-4 |  | To view Profile | Homepage -> My profile
S-5 |  | To view Upcoming review | Homepage -> Upcoming review
S-6 |  | To View Completed review | Homepage -> Completed review
Other details
Author: |  |  | Team Euphoria
Reviewed by: |  |  | Team Euphoria
Approved by:

## Test Case Template
<Project Name><Smoke/Functional/Integration/ System/UAT> Test Cases
Build/Release Version :
Type of Testing: Smoke/Functional/Integration/NFR/System Testing/UAT
Date:
Notes:
(Eg.) 1. This set of test cases should be run to check for the build fitness.
2. The tester should keep the back end (database) available and run an appropriate query to check the results / values displayed against the values shown in the front end.
Scenario ID | Test Case ID | Unit / Module or Location Description | Preconditions | Test Case Description | Test Steps | Test Data | Expected Result | Result (P/F/NT) | Defect ID | Comments
Other details
Author:
Reviewed by:
Approved by:
Test Results Reviewed by:

## Defect Log Template
Defect/Bug Report
Account/ Program Name | Impact training
Project Name: | Training Management System
Defect Id(Required) | Defect Title | Detailed Defect Description | Related Module/Component | Defect Status | Defect Severity | Defect Priority | Defect Environment | Defect Injected Phase | Detected By | Detected in Phase | Detected in Version/Build | Defect Detected On Date | Fixed in version/Build No | Defect Category | Assigned to | Fixed on Date | Estimated Time To fix | Actual Time to Fix | Reopen Count
1 | Validation | Login page not validated | Login | Open | Minor | Medium |  | Release
2 | search | Single word search is not available | search | Fixed | Minor | Medium |  | Release
3 | Search and filter | Search, filter and pagination works only in 1st page | Search | Fixed | Major | High |  | Release
4 | Login | Once loggedout again login is not available | Home | Fixed | Minor | Medium |  | Release
5 | Login | After login only after refresh myprofile and dashboard is visible | Login | Fixed | Critical | Critical |  | Release
5 | Search missing | Search is missing inside departmentlist |  | New | Minor | Low |  | Release
7 | Crud | Crud operations are slow in tms | AddUser | Rejected | Critical | Medium |  | Release
8 | Repetition of datas | Already exixting datas are again added |  | Fixed | Major | High |  | Release
9 | Page loading | page is loading after wrong input(user router ) |  | Open | Minor | Critical |  | Release
10 | Sidebar error | Home button is always active | Sidebar | Fixed | Minor | Low
11 | Navigation error | from other user profile cant navigate to myprofile |  | Fixed | Major | Critical
12 | Image fixing | Image preview, size restriction | EditUser |  | Minor | Low
13 | Breadgrubs | Breadgrubs -> in My profile it displays Head list | Common | Fixed | Major | Medium
14 | Co-Ordinator spelling | spelling Co-Ordinator(from db) |  | Fixed | Minor | Low
15 | Tooltip message | put message in tooltip |  | Fixed | Minor | Medium
16 | Refresh | Edit is working only after refreshing the page |  | Fixed | Critical | Medium
17 | Filter error | Inside filter it shows result for both react and react js | Userlist | Fixed | Minor | Medium
18 |  | change the add button in add trainee | Assigncourse | Fixed | Major | Medium
19 | All users are displaying | For trainee in Completed review it displays all users completed list | ReviewList | Fixed | Major | Critical | [5 empty] | 2022-07-13 |  | Functional Issues |  | 2022-07-17
20 | Naming convention | Change give feedback to viewfeedback | Assigncourse | Fixed | Minor | Medium
21 | Url | Change in Url (defect) |  | Open | Critical | High
22 | Mode Problem | error in offline mode | Schedulereview | Fixed | Major | Critical | [19 empty] | Root cause | Communication Gap
23 | Remove Dashboard | Remove Dashboard from navbar for trainer | Dasboard | Fixed | Minor | Medium | [13 empty] | Defect Status |  | Defect Severity- | Defect Priority | Defect Environment |  |  | Lack of Domain Knowledge
24 | Feedback problem | Give feedback contains default value | TraineeFeedback | Fixed | Major | Critical | [13 empty] | New |  | Critical | High | Development |  |  | Competency
25 | missing breadgrubs and footer | No Breadgrubs and footer for trainer(My course) | TraineeFeedback | Fixed | Minor | Low | [13 empty] | Open |  | Major | Critical | Integration Testing |  |  | Lack of EndUser Input
26 | Submit issue | Could not submit feedback for trainee | TraineeFeedback | Open | Trivial | Medium | [13 empty] | Assigned |  | Minor | Medium | System Testing |  |  | Lack of Standards and Guidelines
27 | Count error | Count is wrong in dashboard(Trainee) | Dashboard | Fixed | Trivial | Critical | [13 empty] | Fixed |  | Trivial | Low | Pre-Production |  |  | Environment
28 | Submit issue | redirection is missing after submit | Coursefeedback | Fixed | Critical | Medium | [13 empty] | Closed |  |  |  | UAT |  |  | Requirements not captured
29 | Upload issue | After uploading no reaction | Courseview/topicview | Fixed | Major | Medium | [13 empty] | Rejected |  | Defect Type |  | Production |  |  | Requirements captured incorrectly
30 | Naming convention | Instead of upcoming review it displays cancelled review | Reviewlist | Fixed | Major | Medium | [13 empty] | Deferred |  | Review |  |  |  |  | Incomplete screen design
31 | Attendance missing | Attendance missing for trainer | Courseview | Open | Major | Critical | [15 empty] | Testing |  |  |  |  | Incorrect screen design
32 | Dashboard issue | Dashboard is not proper for reviewer(including count) | Dashboard | Fixed | Critical | Critical | [20 empty] | Incomplete database design
33 | Added details | Interior details are not displayed in upcoming and completed review | ReviewList | Fixed | Major | Critical | [20 empty] | Incorrect database design
34 | Angular validation missing | Schedule review angular validation not completed | Schedulereview | Fixed | Major | Medium | [20 empty] | Incomplete report layout
35 | unable to add | Add and Edit not proper in user | AddUser | Open | Major | High | [20 empty] | Incorrect report layout
36 | Missing search | Search button is missing inside courselist |  | Fixed | Major | Critical | [20 empty] | Incomplete interface definition
37 | Add trainees to course page incomplete | Add trainees to course page not completed | Assign course | Fixed | Major | Critical | [20 empty] | Incorrect interface definition
38 | topic page incomplete | Add topic page not completed | AddTopic | Fixed | Critical | High | [13 empty] | Defect Injected Phase | Maintenance: | Development | Detected By | Defect Category | Missed Requirements |  | Incomplete security design
39 | Error in edit page | In Edit course It doesnot takes trainer data | Editcourse | Open | Major | Medium | [14 empty] | Requirements | Requirements | QA |  | UI Issues |  | Incorrect security design
40 | Working on review | Schedule review page not completed | Schedulereview | Fixed | Critical | High | [14 empty] | Analysis | Design | Internal Customer |  | Functional Issues |  | Incorrect functionality
41 | Edit MOM incomplete | Edit MOM not completed | ViewMOM | Fixed | Minor | Medium | [14 empty] | Design | Coding | External Customer |  | Performance Issues |  | Incorrect / not optimized SQL
42 | Error on logout(trainer) | Logout is not proper for trainer |  | Fixed | Minor | Low | [14 empty] | coding | Release | Development |  | Non Functional |  | Incorrect logic in design
43 | Trainer flow | Trainer flow not completed(feedback),Completed course |  | New | Critical | High | [14 empty] | Release |  |  |  | Security |  | Incomplete Unit Test Cases
44 | Trainer attendance | Trainer Attendance not completed |  | Open | Critical | High | [18 empty] | Environment Issues |  | Incorrect Unit Test Cases
45 | (Defects in coordinator) | In Department list if we give wrong inputs it doesnt display error message |  | Fixed | Major | Critical | [18 empty] | Upgrade Issue |  | Incomplete Integration Test Cases
46 | Refreshing error | Only after refreshing the page add/edit is displaying(user, course) | courseview | Fixed | Minor | Medium | [18 empty] | Database connectivity issues |  | Incorrect Integration Test Cases
47 | Image problem | While adding user add image first displays cross symbol | Add user | Fixed | Minor | Medium | [18 empty] | Cosmetic issues(Its Comes for Spelling Mistakes and color changes in prompts, It is like minimal changes/) |  | Incomplete Functional Test Cases
48 | Data get(Problem) | While editing course it doesnot takes data from trainer dropdown |  | Fixed | Major | Critical | [18 empty] | Database Error |  | Incorrect Functional Test Cases
49 | Search missing | Course list doesnot contain search | Courselist | Fixed | Minor | Medium | [18 empty] | Data Error |  | Code missing
50 | Missing validation | Add course - Description accepts all kind of data(eg:uyruewruturtuiry) |  | Rejected | Minor | Medium | [18 empty] | Typo Error |  | Incorrect logic in code
51 | Missing validation | Duration - Accepts 2 hrs and not accepts mins |  | Fixed | Major | Critical | [20 empty] | Exception handling error
52 | Consistency misssing | While adding users to course consistency is missing (add button should be at the left and search to the next) |  | Fixed | Major | Medium | [20 empty] | Not a Defect
53 | Topic validation missing | Topic is not validated |  | Fixed | Minor | Medium | [20 empty] | Incomplete Documentation
54 | Error in topic view | after adding topic it doesnot display data |  | Fixed | Major | Critical | [20 empty] | Incorrect Documentation
55 | Nav bar missing | after viewing the topic nav bar is not present |  | Fixed | Minor | Medium | [20 empty] | Scope Change
56 | Topic page error | Edit and disable is not working in topic |  | Fixed | Critical | Critical | [20 empty] | Recommendation
57 | Add assignment details | Inside created topic coordinator should not be able to view assignment details |  | Fixed | Major | Medium | [20 empty] | Incorrect Test Data
58 | (Defects in trainer) | Dashboard is not proper |  | Fixed | Critical | High
59 | Remove button | Inside course list View trainee button should not be present |  | Fixed | Major | Critical
60 | Sidebar missing | Inside topic side bar is not present |  | Fixed | Major | Critical
61 | Assignment not completed | Uploading assignment is not working |  | Fixed | Critical | High
62 | Refreshing error | If topic page is refreshed all the datas are going |  | Fixed | Major | Critical
63 | Consistency misssing | consistency missing in topic list |  | Fixed | Minor | Critical
64 | Add pointer | pointer should be present for assignment |  | Fixed | Minor | Critical
65 | Add some details | Submitted on can be viewed |  | Fixed | Minor | Medium
66 | Remove header | 2 headers are there in giving assignment |  | Fixed | Major | Critical
67 | (Defects in trainee) | Inside feedback if i add or edit, it navigates to blank page |  | Fixed | Major | Critical
68 | Feedback validation | Feedback page is not validated and doesnot shows error message |  | Open | Major | Critical
69 | (Defects in reviewer) | Inside dashboard image and role is not there |  | Fixed | Major | Critical
70 | MOM missing | Reviewer is not able to view MoM |  | Open | Major | Critical
71 | Search solved with bug | Search and department together doesnot work |  | Fixed | Major | Critical
72 | Topic validation missing | validation in topic(not showing validation error message) |  | Fixed | Minor | Medium
73 | Error in API | Multiple time disable is working(department) |  | Open | Critical | High
74 | Error in API | Already disable error should be shown(Topic,course) |  | Open | Major | Critical
75 | Error in API | Already Assigned user doesnot shows error message |  | Open | Major | Critical
76 | Course trainee edit | Save button should be positioned, add button should changed as select, take pagination, scroll bar hide when less item, disable should contain draft before removing it) |  | Fixed | Minor | Low
77 | change font size | font size in topic(done) |  | Fixed | Minor | Medium
78 | Consistency missing | attendance no red and green color(card size big but font is small) |  | Fixed | Major | Critical
79 | consistency missing | trainer/trainee (course topic list not be centralized) |  | Fixed | Major | Medium
80 | add more details | add created on, view ,name in list card |  | Fixed | Major | Medium
81 | Assignment error | submitted assignment should be enabled after the assignment submitted |  | Fixed | Major | Critical
82 | Topic assignment error | topic assignment not displaying in assigned one |  | Open | Major | Critical
83 | Course heading missing | course name not shown in the feedback |  | Fixed | Minor | Medium
84 | Fix placeholder | Add topic (Placeholder should contain example ) |  | Fixed | Minor | Medium
85 | Bug in assignment | While creating new assignment autogeneration of topic is available |  | Fixed | Major | Critical
86 | Remove edit in feedback | Feedback should not be editable |  | Open | Major | Critical
87 | Edit password | User password could not be edited |  | Open | Critical | High
88 | Trainee feedback | Trainee feedback not completed |  | Open | Major | Critical
89 | Trainer attendance | Trainer could not mark attendance |  | Open | Critical | High
90 |  | Update title in Add user page |  | Fixed
91 |  | Order the courses to the latest |  | Fixed
92 |  | Add and select misaline | Assign course | Open
93 |  | Attendance (topic details can be added)
94 |  | Coursetrainee (spacing between button) |  | Fixed
95 | Validation in feedback | trainer should not provide feedback before completing course
96 |  | Add no assignment submitted yet (if trainee doesnot submit assignment) |  | Open
97 |  | Created on date should be changed(while trainee submitting assignment) |  | Fixed
98 |  | before attendance assignment should not be marked |  | Open
99 |  | Toaster to mark attendance |  | Fixed
100 |  | get methods should be validated(url) |  | Open
101 |  | If assignments are not assigned do not show the header |  | Open
102 |  | If trainee provided feedback he could not be removed from course list |  | Open
103 |  | consistency missing(no file chosen & upload image) |  | Fixed
104 |  | Feedback contains bug |  | Open
105 | optional | Add move to department(trainee)
106 |  | Edit is not working for users
107 |  | Course trainee page not working properly
108 |  | Order the courses to the latest
Inside MOM department should be added